## Sheet1 (hidden)
E3 Lookup | NeededNeeded | Needed | Needed | Needed
In ProgressIn Progress | In Progress
In ProgressNeeded | In Progress
In ProgressReady | In Progress
NeededIn Progress | In Progress
NeededNeeded | Needed
NeededReady | In Progress
Ready In Progress | In Progress
Ready Needed | In Progress
Ready Ready | Ready
B9 Lookup | NeededNeeded | Needed
In ProgressIn Progress | In Progress
In ProgressNeeded | In Progress
In ProgressReady | In Progress
NeededIn Progress | In Progress
NeededNeeded | Needed
NeededReady | In Progress
Ready In Progress | In Progress
Ready Needed | In Progress
Ready Ready | Ready
E13 Lookup | NeededNeeded | Needed
In ProgressIn Progress | In Progress
In ProgressNeeded | In Progress
In ProgressReady | In Progress
NeededIn Progress | In Progress
NeededNeeded | Needed
NeededReady | In Progress
Ready In Progress | In Progress
Ready Needed | In Progress
Ready Ready | Ready
E15 Lookup | NeededNeeded | Needed
In ProgressIn Progress | In Progress
In ProgressNeeded | In Progress
In ProgressReady | In Progress
NeededIn Progress | In Progress
NeededNeeded | Needed
NeededReady | In Progress
Ready In Progress | In Progress
Ready Needed | In Progress
Ready Ready | Ready
C15 Lookup | NeededNeeded | Needed
In ProgressIn Progress | In Progress
In ProgressNeeded | In Progress
In ProgressReady | In Progress
NeededIn Progress | In Progress
NeededNeeded | Needed
NeededReady | In Progress
Ready In Progress | In Progress
Ready Needed | In Progress
Ready Ready | Ready
E31 Lookup | NeededNeeded | Needed
In ProgressIn Progress | In Progress
In ProgressNeeded | In Progress
In ProgressReady | In Progress
NeededIn Progress | In Progress
NeededNeeded | Needed
NeededReady | In Progress
Ready In Progress | In Progress
Ready Needed | In Progress
Ready Ready | Ready
E37 Lookup | NeededNeeded | Needed
In ProgressIn Progress | In Progress
In ProgressNeeded | In Progress
In ProgressReady | In Progress
NeededIn Progress | In Progress
NeededNeeded | Needed
NeededReady | In Progress
Ready In Progress | In Progress
Ready Needed | In Progress
Ready Ready | Ready
E39 Lookup | NeededNeeded | Needed
In ProgressIn Progress | In Progress
In ProgressNeeded | In Progress
In ProgressReady | In Progress
NeededIn Progress | In Progress
NeededNeeded | Needed
NeededReady | In Progress
Ready In Progress | In Progress
Ready Needed | In Progress
Ready Ready | Ready
C21 Lookup | NeededNeeded | Needed
In ProgressIn Progress | In Progress
In ProgressNeeded | In Progress
In ProgressReady | In Progress
NeededIn Progress | In Progress
NeededNeeded | Needed
NeededReady | In Progress
Ready In Progress | In Progress
Ready Needed | In Progress
Ready Ready | Ready
E21 Lookup | NeededNeeded | Needed
In ProgressIn Progress | In Progress
In ProgressNeeded | In Progress
In ProgressReady | In Progress
NeededIn Progress | In Progress
NeededNeeded | Needed
NeededReady | In Progress
Ready In Progress | In Progress
Ready Needed | In Progress
Ready Ready | Ready

## Cover Letter
Acknowledgement: The TST was developed for NC Medicaid by NC AHEC and may be copied without permission in its entirety.
Acknowledgement: The TST was developed for NC Medicaid by NC AHEC and may be copied without permission in its entirety.
Tool Instructions
| PRACTICE NAME: | ACME Happy Practice | Step 1: Download and save this file with a new name of your choice. Be sure to remember where you saved the file i.e. on your desktop, in a folder, under My Documents. Step 2: Complete practice specific information on Cover Letter worksheet. Include your current number of active Medicaid patients and all PHP Plans your practice plans to contract. Step 3: Review Timeline for a quick reference to milestone dates during the launch of Medicaid Managed Care. Step 4: Determine your method for completing this tool. A printable version of the gap analysis is available under Printable Gap. To complete the tool electronically and take advantage of the features to auto populating the TST Tool Dashboard, continue to Front Admin Gap. Step 5: Gather a team from your practice to work with you on this tool. The number of people on the team is your preference. Be sure to include staff that have an understanding of your practice processes for patient scheduling, building a new insurance, EHR documentation, management and clinical flow. Step 6: Complete the questions in the Gap tool(s) for the columns: E- Practice or CIN?, F- Status, K- Actions Required and L- Due Date. Step 7: Review Attestation section to confirm requirements for AMH Tier 3. Review TST Tool Dashboard to view your current readiness status. This tool will continue to update as you move from Needed to In Progress to Ready on the Gaps. The first step must be satisfied in order to pass to the next. Step 8: Assess actions required and review your status on a regular basis. A Project Plan section is available for you to develop your own timeline on accomplishing your readiness.
ADDRESS:
CONTACT NAME:
EMAIL:
MEDICAID (MCT) #:
# OF MEDICAID PATIENTS:
AMH TIER:
CIN:
PHP CONTRACTED 1:
PHP CONTRACTED 2:
PHP CONTRACTED 3:
PHP CONTRACTED 4:
PHP CONTRACTED 5:
Important Webpages & Resource Quick Links
NC Medicaid Transformation Main Site |  | NC Medicaid MCT Training |  | NC Medicaid Quality Strategy Page
https://medicaid.ncdhhs.gov/transformation |  | https://medicaid.ncdhhs.gov/providers/provider-playbook-medicaid-managed-care/provider-playbook-training-courses |  | https://medicaid.ncdhhs.gov/transformation/quality-management-and-improvement
NC Medicaid AMH Provider Manual |  | NC Medicaid Transformation Provider Playbook |  | Health Plan Contacts & Resources Page
https://files.nc.gov/ncdma/documents/Providers/Programs_Services/amh/AMH-Provider-Manual-12.12.2019.pdf |  | https://medicaid.ncdhhs.gov/providers/provider-playbook-medicaid-managed-care |  | https://medicaid.ncdhhs.gov/transformation/health-plans/health-plan-contacts-and-resources
NC Medicaid AMH Training Page |  | Plan Enrollment Site
https://medicaid.ncdhhs.gov/transformation/advanced-medical-home/advanced-medical-home-training |  | https://ncmedicaidplans.gov/
  AMH Tier Support Tool Cover Letter

## Timeline
  NC Medicaid Managed Care Timeline

## Printable Gap
Standard | Area | Step ID # | Requirement | Practice or CIN? | Needed | In-Progress | Ready | Actions Required | Due Date
Access-After Hours Communication | Administrative | A1T2 | Does the practice currently offer an after hours phone line with automated recording and the ability to leave a message?
| Administrative | A2T2 | Does the 24 hour access after hours on-call phone line include access that will connect to a clinical representative within 30 minutes?
| Administrative | A3T2 | Does the practice offer 24 hour access with an after hour on call phone line that will connect to a real person and page on-call provider?
| Administrative | A4T3 | Does the practice offer 24 hour access with an after hour on call phone line that will connect to a clinical representative or provider on-call?
Access-Hours of Operation | Administrative | A5T2 | Is the practice open normal business hours and provides a phone line for after hours calls?
| Administrative | A6T2 | Does the practice have the ability to measure wait time for appointment availability?
| Administrative | A7T2 | Does the practice set appointment availability goals to PHP/DHB Appointment Access & Availability Standards and is working to meet goals?
| Administrative | A8T3 | Does the practice meet PHP/DHB Appointment Access & Availability Standards?
| Administrative | A9T3 | Does the practice offer improved access through same day appointments and expanded hours or alternative appointment types (telemedicine)?
Billing & Claims Readiness | Billing/Claims | B1T2 | Are all contracted PHP insurances built into the practice management system?
| Billing/Claims | B2T2 | Has the practice determined the process for where payments from PHPs will be received for Patient Visits & Services?
| Billing/Claims | B3T2 | Has the practice reviewed the process for receiving patient EOBs?
| Billing/Claims | B4T3 | Tier 3 ONLY - Has the practice determined the process for where payments from PHPs will be received for (PMPM Care Management Fee) Care Management Services?
| Billing/Claims | B5T3 | Tier 3 ONLY - Has the practice determined the process for where payments from PHPs will be received for Quality Incentives (Performance Incentive Payments)?
Eligibility Check | Front Office | EG1T2 | Have office staff been trained on how to verify and document insurance information (eligibility, PHP, PCP, etc.?) before or at patient check-in?
| Front Office | EG2T2 | Has the office staff been trained on when or how often to check eligibility for the new PHP plans? If practice has auto verification of eligibility available in practice management system, has this feature been updated to include the new PHPs?
| Front Office | EG3T2 | Has the practice successfully checked eligibility on Medicaid Managed Care Plan test patients?
PHP Identification & Onboarding | Front Office | F1T2 | Do the front office staff know which PHPs are in-network with your practice?
| Front Office | F2T2 | Have the front desk staff been trained on identifying each PHP insurance card?
| Front Office | F3T2 | Has the office staff been trained on how enrollees are assigned to PCPs, and how to assist enrollees in requesting a change to their PCP?
| Administrative | F4T2 | Are all contracted PHP insurances built into the practice management system?
Practice Management- PHP Participation | Administrative | F5T2 | Has the practice contracted with each PHP that the practice wants to be in-network with or are agreements are being reviewed/discussed?
| Administrative | F6T2 | Does the practice have access to each in-network PHP Provider Manual for review? Do front office staff know which PHPs are in-network with your practice?
| Administrative | F7T2 | Has the practice completed PHP Orientation & Training?
Practice Management- Quality Strategy | Administrative | Q1T2 | Has the practice reviewed the Medicaid Managed Care Quality Strategy?
| Administrative | Q2T2 | Can the practice locate/access quality reports provided by their in-network PHP plans?
| Administrative | Q3T2 | Can the practice locate/access quality reports within their EHR system?
| Administrative | Q4T3 | Tier 3 ONLY - Has the practice determined who will receive quality & cost reports from the PHPs?
| Administrative | Q5T3 | Tier 3 ONLY - Has the practice determined who is going to receive the reports for quality and/or care gaps provided by the CIN/PHP?
| Administrative | Q6T2 | Has the practice reviewed each PHP quality standard requirements and know the process for receiving reports?
Care Management Enrollment | Clinical Care Team | C1T2 | Can the practice receive encounter data/cost reports from PHP on high-risk patients eligible for care management?
| Clinical Care Team | C2T2 | Has the practice has determined enrollment criteria for referral or enrollment in care management?
| Clinical Care Team | C3T2 | Does the practice include high-risk reports, HCC scores, Co-Morbidity Diagnosis and/or prevalence of social determinates in care management referral criteria?
| Clinical Care Team | C4T3 | Does the practice use care management enrollment criteria to stratify patients by risk levels and incorporates risk reports in all aspects of patient care? Does the practice have a designated staff member to receive and compile PHP risk scoring results?
| Administrative | C5T3 | Tier 3 ONLY - Has the practice determined who will receive and compile PHP Risk Scoring results?
Care Management Process | Clinical Care Team | C6T2 | Has the practice determined a communication workflow between the PCP and the assigned Care Manager?
| Clinical Care Team | C7T2 | Has the practice determined a process for patient referral to care management services? Does the practice include communication workflow between the PCP and the assigned Care Manager as part of the process?
| Clinical Care Team | C8T2 | Does the practice use a formalized workflow for referring patients to care management and tracks referrals to ensure patients are using the service?
| Clinical Care Team | C9T3 | Does the practice use CIN or care management organization to provide care management services to patients internally in their practice? Are Care Plans sent electronically to primary care provider after each appointment?
| Clinical Care Team | C9T4 | Does the practice have a Care Manager on site to provide services to enrolled patients? Are Care Plans documented in the practice EHR and reviewed/updated at least annually with the patient and primary care provider?
Cultural Competency | Administrative | CU1T2 | Does the practice include cultural competency training to all staff annually?
| Administrative | CU2T2 | Does the practice include cultural competency training to all staff annually and incorporates cultural competency in patient communication?
| Administrative | CU3T2 | Does the practice include cultural competency training to all staff quarterly, incorporates cultural competency in patient communication every day and uses cultural competent language/material when providing written materials to patients?
Patient Documentation Requirements | Clinical Care Team | DOC1 | Place Holder Here
| Clinical Care Team | DOC2 | Place Holder Here
| Clinical Care Team | DOC3 | Adults Only -Do you have a process for asking patients about Advance Directives or a Living Will? Do you have resources available for patients in need to help in creating one?
| Clinical Care Team | DOC4 | Is the practice able to perform and document a Comprehensive Assessment as part of a clinician visit, or separately by a team led by a clinician with a minimum credential of RN or LCSW? (attach link to understanding Comp Assess)
Population Health-Empanelment | Clinical Care Team | EP1 | Does the practice know their current Medicaid attribution or have a report of current Medicaid active patients?
| Clinical Care Team | EP2 | Does the practice have a process for accepting new patients, opening and closing panels, and panel size?
| Clinical Care Team | EP3 | Does the practice instruct current Medicaid patients on the meaning of a Primary Care Provider? Does the practice work to ensure all current active Medicaid patients have had an appointment/service within the past year?
| Clinical Care Team | EP4 | Does the practice have a attributed patient lists from each in-network PHP? Does the practice use those attribution lists to determine new attributed patients, incorrect attributed patients and general additonal workload during the first months of Managed Care?
| Clinical Care Team | EP5 | Has the practice reconciled the PHP patient attribution list with the practice's EHR patient panel list. Are the patient panel lists up to date in the EHR? Does the practice have a policy in place to determine process and frequency of reconciling the panel lists?
Language Line | Administrative | LL1T2 | Is the practice aware of PHP language line resources?
| Administrative | LL2T2 | Is the practice ready to use PHP language line resources when requested by provider during an appointment?
| Administrative | LL3TT2 | Does the practice pro-actively includes patient primary language in pre-visit planning to schedule interpreter services during the patient visit?
Referral Management | Clinical Care Team | REF1T2 | Is the PCP prepared to take on referral determination for all referral decisions related to the patient?
| Clinical Care Team | REF2T2 | Does the practice understand which PHP plans require prior authorization for referrals to specialists?
| Clinical Care Team | REF3T2 | Are clinical providers & referral coordinators aware of common referral providers that are in-network with patient plans?
| Clinical Care Team | REF4T3 | Does the practice have a process to track referrals to ensure completion and that the consult note has been received and reviewed by the ordering provider? Is there a policy in place outlining this process?
SDOH In Action | Administrative | SD1T2 | Tier 3 ONLY - Has the practice determined who will receive "Care Needs Screening" reports and how those are going to be documented in the EHR and communicated to the PCP provider?
| Clinical Care Team | SD2T2 | Does the clinical team have training on understanding Social Determinants of Health as it relates to Medicaid Managed Care?
| Clinical Care Team | SD3T2 | Is the practice connected with NCCARE360?
| Clinical Care Team | SD4T3 | Does the clinical team have access to NCCARE360?
Health Information Exchange | Clinical Care Team | TC1T2 | Is the practice connected with NC HealthConnex?
| Clinical Care Team | TC2T2 | Does the clinical team have access to the NC HealthConnex Portal?
| Clinical Care Team | TC3T3 | Tier 3 ONLY - Has the practice enrolled in NC* Notify?
| Clinical Care Team | TC4 | Tier 3 ONLY - Has the practice determined the workflow for monitoring and integrating ADT Data Feeds in transitional care management?
Transitional Care Management | Clinical Care Team | TCM1 | Is the practice is working on establishing a system for regularly receiving information from hospitals about discharges and ED visits so that follow up can consistently occur. Does the practice have a policy in place that outlines the process?
| Clinical Care Team | TCM2 | Does the practice follow up with patients within a designated time interval after an emergency room visit or hospital discharge? Does the practice implement a workflow to utilize TCM codes?
| Clinical Care Team | TCM3 | Is the practice consistently following up with patients within a designated time interval after an emergency room visit or hospital discharge. Does the practice consistently utilizes TCM codes?
Patient Value Added Services | Clinical Care Team | V3 | Are clinical providers informed on the new paid behavioral health services for patients through their new PHP?
| Clinical Care Team | V4 | Are clinical providers informed on the additional paid services for patients through their new PHP?
| Clinical Care Team | V5 | Is the practice is aware of PHP Value Added Services and will recommend these services to patients in Medicaid Managed Care when clinically necessary?
| Clinical Care Team | V6 | Does the practice understand how the PHP Value Added services have an effect on payments in the Quality Strategy for Medicaid Managed Care. Practice is prepared to utilize or refer patients to these resources with treatment when clinically necessary?
Vaccine Management | Clinical Care Team | VC1 | Does the practice currently offer vaccinations in the office -OR- refers patients to their local health department or another entity for vaccinations and follows-up to ensure that it has been completed?
| Clinical Care Team | VC2 | Does the practice understand how vaccination status has an effect on the Quality Strategy in Medicaid Managed Care? Is the practice prepared to complete work around closing care gaps for patients in need of vaccinations?
  PRINTABLE GAP

## Front Admin Gap
Index | Standard | Area | Step ID # | Requirement | Practice or CIN? | Status | Tier Level | Test | PCMH Crosswalk | Rationale | Actions Required | Due Date
1 | Access-After Hours Communication | Administrative | A1T2 | Does the practice currently offer an after hours phone line with automated recording and the ability to leave a message? |  | Needed | Tier 2 |  |  | PHP Provider Manuals include a table outlining Appointment Access Standards. Access Standards for Tier 2 and 3 will be the same as Carolina Access II standards around after-hours availability, panel size, the availability of interpretation services, hours of operation, and the availability of certain preventive and ancillary services that vary by age.
2 | Access-After Hours Communication | Administrative | A2T2 | Does the 24 hour access after hours on-call phone line include access that will connect to a clinical representative within 30 minutes? |  | Needed | Tier 2 |  |  | This requirement is the same as Carolina Access II requirements.
3 | Access-After Hours Communication | Administrative | A3T2 | Does the practice offer 24 hour access with an after hour on call phone line that will connect to a real person and page on-call provider? |  | Needed | Tier 2 |  |  | This requirement is the same as Carolina Access II requirements.
4 | Access-After Hours Communication | Administrative | A4T3 | Does the practice offer 24 hour access with an after hour on call phone line that will connect to a clinical representative or provider on-call? |  | Needed | Tier 3 |  |  | This requirement is the same as Carolina Access II requirements.
5 | Access-Hours of Operation | Administrative | A5T2 | Is the practice open normal business hours and provides a phone line for after hours calls? |  | Needed | Tier 2 |  |  | The PHP Provider Manuals include a table outlining the Appointment availability standards and in some cases wait time. This requirement is the same as Carolina Access II standards around after-hours availability, panel size, the availability of interpretation services, hours of operation, and the availability of certain preventive and ancillary services that vary by age.
6 | Access-Hours of Operation | Administrative | A6T2 | Does the practice have the ability to measure wait time for appointment availability? |  | Needed | Tier 2 |  |  | The practice will need to show wait time for appointments as well as number of days until an appointment is available when requested by the PHP.
7 | Access-Hours of Operation | Administrative | A7T2 | Does the practice set appointment availability goals to PHP/DHB Appointment Access & Availability Standards and is working to meet goals? |  | Needed | Tier 2 |  |  | Review Provider Manuals on Access and Availability Standards.
8 | Access-Hours of Operation | Administrative | A8T3 | Does the practice meet PHP/DHB Appointment Access & Availability Standards? |  | Needed | Tier 3 |  |  | Review Provider Manuals on Access and Availability Standards.
9 | Access-Hours of Operation | Administrative | A9T3 | Does the practice offer improved access through same day appointments and expanded hours or alternative appointment types (telemedicine)? |  | Needed | Tier 3 |  |  | Under the Access and Availability Standards, a practice must be able to see a patient with urgent needs within 24 hours. Having same day open appointments or an alliterative appointment type such as telemedicine can help to meet this requirement.
10 | Billing & Claims Readiness | Billing/Claims | B1T2 | Are all contracted PHP insurances built into the practice management system? |  | Needed | Tier 2 |  |  | When the front office chooses the insurance under registration, they may find several of the same named plans that are commercial. Consider naming these insurances in the system so that they are easily recognizable. One way to do this is to put NC Medicaid at the front or end of the insurance name.
11 | Billing & Claims Readiness | Billing/Claims | B2T2 | Has the practice determined the process for where payments from PHPs will be received for Patient Visits & Services? |  | Needed | Tier 2
12 | Billing & Claims Readiness | Billing/Claims | B3T2 | Has the practice reviewed the process for receiving patient EOBs? |  | Needed | Tier 2
13 | Billing & Claims Readiness | Billing/Claims | B4T3 | Tier 3 ONLY - Has the practice determined the process for where payments from PHPs will be received for (PMPM Care Management Fee) Care Management Services? |  | Needed | Tier 3
14 | Billing & Claims Readiness | Billing/Claims | B5T3 | Tier 3 ONLY - Has the practice determined the process for where payments from PHPs will be received for Quality Incentives (Performance Incentive Payments)? |  | Needed | Tier 3
15 | Front Office - Member Eligibility | Front Office | EG1T2 | Have office staff been trained on how to verify and document insurance information (eligibility, PHP, PCP, etc.?) before or at patient check-in? |  | Needed | Tier 2
16 | Front Office - Member Eligibility | Front Office | EG2T2 | Has the office staff been trained on when or how often to check eligibility for the new PHP plans? If practice has auto verification of eligibility available in practice management system, has this feature been updated to include the new PHPs? |  | Needed | Tier 2
17 | Front Office - Member Eligibility | Front Office | EG3T2 | Has the practice successfully checked eligibility on Medicaid Managed Care Plan test patients? |  | Needed | Tier 2
18 | PHP Identification & Onboarding | Front Office | F1T2 | Do the front office staff know which PHPs are in-network with your practice? |  | Needed | Tier 2
19 | PHP Identification & Onboarding | Front Office | F2T2 | Have the front desk staff been trained on identifying each PHP insurance card? |  | Needed | Tier 2 |  |  | NC Medicaid Beneficiary Enrollment Webpage
20 | PHP Identification & Onboarding | Front Office | F3T2 | Has the office staff been trained on how enrollees are assigned to PCPs, and how to assist enrollees in requesting a change to their PCP? |  | Needed | Tier 2
21 | PHP Identification & Onboarding | Administrative | F4T2 | Are all contracted PHP insurances built into the practice management system? |  | Needed | Tier 2
22 | Practice Management- PHP Participation | Administrative | F5T2 | Has the practice contracted with each PHP that the practice wants to be in-network with or are agreements are being reviewed/discussed? |  | Needed | Tier 2
23 | Practice Management- PHP Participation | Administrative | F6T2 | Does the practice have access to each in-network PHP Provider Manual for review? Do front office staff know which PHPs are in-network with your practice? |  | Needed | Tier 2
24 | Practice Management- PHP Participation | Administrative | F7T2 | Has the practice completed PHP Orientation & Training? |  | Needed | Tier 2 |  |  | Each PHP will require that the practice complete orientation & training during the initial enrollment in the PHP.
25 | Practice Management- Quality Strategy | Administrative | Q1T2 | Has the practice reviewed the Medicaid Managed Care Quality Strategy? |  | Needed | Tier 2
26 | Practice Management- Quality Strategy | Administrative | Q2T2 | Can the practice locate/access quality reports provided by their in-network PHP plans? |  | Needed | Tier 2
27 | Practice Management- Quality Strategy | Administrative | Q3T2 | Can the practice locate/access quality reports within their EHR system? |  | Needed | Tier 2
28 | Practice Management- Quality Strategy | Administrative | Q4T3 | Tier 3 ONLY - Has the practice determined who will receive quality & cost reports from the PHPs? |  | Needed | Tier 3
29 | Practice Management- Quality Strategy | Administrative | Q5T3 | Tier 3 ONLY - Has the practice determined who is going to receive the reports for quality and/or care gaps provided by the CIN/PHP? |  | Needed | Tier 3
30 | Practice Management- Quality Strategy | Administrative | Q6T2 | Has the practice reviewed each PHP quality standard requirements and know the process for receiving reports? |  | Needed | Tier 2 |  |  | Quality Standards for Tier 2 are located in the PHP Provider Manuals. They are the same as the Carolina Access II standards around after-hours availability, panel size, the availability of interpretation services, hours of operation, and the availability of certain preventive and ancillary services that vary by age. Tier 3 Standards are added and can be found in the Tier 3 attestation.
      FRONT ADMIN GAP

## Clinical Admin Gap
Index_CA | Standard | Area | Step ID # | Requirement | Practice or CIN? | Status | Tier Level | PCMH Crosswalk | Rationale | Actions Required | Due Date
2 | Care Management Enrollment | Clinical Care Team | C1T2 | Can the practice receive encounter data/cost reports from PHP on high-risk patients eligible for care management? |  | Needed | Tier 2
3 | Care Management Enrollment | Clinical Care Team | C2T2 | Has the practice determined enrollment criteria for referral or enrollment in care management? |  | Needed | Tier 2 | NCQA CM01
4 | Care Management Enrollment | Clinical Care Team | C3T2 | Does the practice include high-risk reports, HCC scores, Co-Morbidity Diagnosis and/or prevalence of social determinates in care management referral criteria? |  | Needed | Tier 2 | NCQA CM03
5 | Care Management Enrollment | Clinical Care Team | C4T3 | Does the practice use care management enrollment criteria to stratify patients by risk levels and incorporates risk reports in all aspects of patient care? Does the practice have a designated staff member to receive and compile PHP risk scoring results? |  | Needed | Tier 3 | NCQA CM03 | PHPs will be responsible for using their plan-specific risk scoring methodologies to identify members of "priority populations" and assign risk scores to all PHP members. PHPs will share risk scoring results and information on priority populations with all practices. Tier 3 AMHs must use the risk score as part of their process to stratify their patient panels and identify patients who would benefit from care management.
6 | Care Management Enrollment | Administrative | C5T3 | Tier 3 ONLY - Has the practice determined who will receive and compile PHP Risk Scoring results? |  | Needed | Tier 3
7 | Care Management Process | Clinical Care Team | C6T2 | Has the practice determined a communication workflow between the PCP and the assigned Care Manager? |  | Needed | Tier 2
8 | Care Management Process | Clinical Care Team | C7T2 | Has the practice determined a process for patient referral to care management services? Does the practice include communication workflow between the PCP and the assigned Care Manager as part of the process? |  | Needed | Tier 2
9 | Care Management Process | Clinical Care Team | C8T2 | Does the practice use a formalized workflow for referring patients to care management and tracks referrals to ensure patients are using the service? |  | Needed | Tier 2
10 | Care Management Process | Clinical Care Team | C9T3 | Does the practice use a CIN, care management organization or has hired a staff member to provide care management services to patients internally in their practice? Are Care Plans sent electronically to primary care provider after each appointment? |  | Needed | Tier 3
1 | Care Management Process | Clinical Care Team | C9T4 | Does the practice have a Care Manager on site with a minimum credential of RN, LCSW or is supervised by a MD to provide services to enrolled patients? Are Care Plans documented in the practice EHR and reviewed/updated at least annually with the patient and primary care provider? Does the practice have a policy in place that outlines the care management process and requirements? |  | Needed | Tier 3 | NCQA TC 02, CM01, CM03, CM04, CM 05, CM06, CM07, CM08
11 | Cultural Competency | Administrative | CU1T2 | Does the practice include cultural competency training to all staff annually? |  | Needed | Tier 2 |  | Review PHP Provider Manuals for more information on cultural competency training requirements. Cultural Competency is defined as "the ability to understand, appreciate and interact effectively with people of different cultures and/or beliefs to ensure the needs of the individuals are met. The ability to interact effectively with people of different cultures, helps to ensure the needs of all community members are addressed. It also refers to such characteristics as age, gender, sexual orientation, disability, religion, income level, education, geographical location, or profession. Cultural competency means to be respectful and responsive to the health beliefs and practices and cultural and linguistic needs of diverse populations groups."
12 | Cultural Competency | Administrative | CU2T2 | Does the practice include cultural competency training to all staff and incorporates cultural competency in patient communication? |  | Needed | Tier 2 |  | Schedule staff training on how to address cultural competency in communication with patients.
13 | Cultural Competency | Administrative | CU3T2 | Does the practice include cultural competency training to all staff regularly, incorporates cultural competency in patient communication every day and uses cultural competent language/material when providing written materials to patients? |  | Needed | Tier 2 |  | Review written material from the practice to ensure cultural competency.
16 | Patient Documentation Requirements | Clinical Care Team | DOC3 | Adults Only -Do you have a process for asking patients about Advance Directives or a Living Will? Do you have resources available for patients in need to help in creating one? |  | Needed | Tier 2 | NCQA KM 02
17 | Patient Documentation Requirements | Clinical Care Team | DOC4 | Is the practice able to perform and document a Comprehensive Assessment as part of a clinician visit, or separately by a team led by a clinician with a minimum credential of RN or LCSW? (attach link to understanding Comp Assess) |  | Needed | Tier 2 | NCQA KM 02, KM03, KM04, KM07,KM14 | Review AMH Provider Manual Attestation Table for more information on Comprehensive Assessment requirements.
18 | Population Health-Empanelment | Clinical Care Team | EP1 | Does the practice know their current Medicaid attribution or have a report of current Medicaid active patients? |  | Needed | Tier 2 |  | It is important for a practice to understand their current active number of attributed patients. This will assist the practice in estimating future attribution numbers, the workload capacity at go-live and PMPM estimated payments.
19 | Population Health-Empanelment | Clinical Care Team | EP2 | Does the practice have a process for accepting new patients, opening and closing panels, and panel size? |  | Needed | Tier 2 |  | Consult your PHP contacts for details on contracted panel size, age ranges and accepting new members. Review AMH 101 Presentation, Especially slide 10 for a breakdown of tier levels, services & PMPM rates.
20 | Population Health-Empanelment | Clinical Care Team | EP3 | Does the practice instruct current Medicaid patients on the meaning of a Primary Care Provider? Does the practice work to ensure all current active Medicaid patients have had an appointment/service within the past year? |  | Needed | Tier 2 |  | During auto-assignment, criteria such as past submitted claims will be used to determine where a patient is assigned. You want to be sure that all of your patients have had at least one claim in the past year at your practice.
21 | Population Health-Empanelment | Clinical Care Team | EP4 | Does the practice have a attributed patient lists from each in-network PHP? Does the practice use those attribution lists to determine new attributed patients, incorrect attributed patients and general additional workload during the first months of Managed Care? |  | Needed | Tier 2 | NCQA- AC14 | Review Timeline for when auto attribution ends. Sometime after and before the go-live date of July 01, 2021 practices will receive their final attribution list.
22 | Population Health-Empanelment | Clinical Care Team | EP5 | Has the practice reconciled the PHP patient attribution list with the practice's EHR patient panel list. Are the patient panel lists up to date in the EHR? Does the practice have a policy in place to determine process and frequency of reconciling the panel lists? |  | Needed | Tier 3 |  | Reconciling lists will assist your practice in determining workload capacity during the first months of go-live. Note new patients that will need to have an appointment and high risk patients that will be enrolled in care management.
23 | Language Line | Administrative | LL1T2 | Is the practice aware of PHP language line resources? |  | Needed | Tier 2 |  | Review each PHP Provider Manual for information on language line resources.
24 | Language Line | Administrative | LL2T2 | Is the practice ready to use PHP language line resources when requested by provider during an appointment? |  | Needed | Tier 2 |  | Consider making a table for each contact number.
25 | Language Line | Administrative | LL3TT2 | Does the practice pro-actively includes patient primary language in pre-visit planning to schedule interpreter services during the patient visit? |  | Needed | Tier 2
26 | Referral Management | Clinical Care Team | REF1T2 | Is the PCP prepared to take on referral determination for all referral decisions related to the patient? |  | Needed | Tier 2
27 | Referral Management | Clinical Care Team | REF2T2 | Does the practice understand which PHP plans require prior authorization for referrals to specialists? |  | Needed | Tier 2 |  | PHP Provider Manuals contain details on Prior authorization requirements.
28 | Referral Management | Clinical Care Team | REF3T2 | Are clinical providers & referral coordinators aware of common referral providers that are in-network with patient plans? |  | Needed | Tier 2 |  | Specialists will also need to contract with the new PHP plans.
29 | Referral Management | Clinical Care Team | REF4T3 | Does the practice have a process to track referrals to ensure completion and that the consult note has been received and reviewed by the ordering provider? Is there a policy in place outlining this process? |  | Needed | Tier 3
31 | SDOH In Action | Clinical Care Team | SD2T2 | Does the clinical team have training on understanding Social Determinants of Health as it relates to Medicaid Managed Care? |  | Needed | Tier 2 |  | It is important for care team members to have a basic understanding of social determinants of health, or un-met resource needs, and how this area can have a negative impact on a patient's health. Data on this information including food insecurity, un-met housing issues, exposure to violence and transportation needs will be provided to the care team for patients in Medicaid Managed Care. There will also be resources available to help aide in getting patients the resources that they need. | Review "Using Standardized Social Determinants of Health Screening Questions to Identify and Assist Patients with Unmet Health-related Resource Needs in North Carolina"
32 | SDOH In Action | Clinical Care Team | SD3T2 | Is the practice connected with NCCARE360 or has knowledge of ways to connect patients to unmet health-related resource needs? |  | Needed | Tier 2 |  | https://nccare360.org/
33 | SDOH In Action | Clinical Care Team | SD4T3 | Does the clinical team have access to NCCARE360 or engage with patients in connecting them to area community resources? |  | Needed | Tier 3
30 | SDOH In Action | Administrative | SD5T2 | Tier 3 ONLY - Has the practice determined who will receive "Care Needs Screening" reports and how those are going to be documented in the EHR and communicated to the PCP provider? |  | Needed | Tier 3 |  | The Care Needs Screening helps identify enrollees in need of a Comprehensive Assessment for care management. Minimum Care Needs Screening Requirements include chronic or acute conditions (including chronic pain), behavioral health needs, medications, other factors or conditions which the PHP would need to be aware to inform interventions, and unmet health-related resource needs (aka social determinants of health), including housing, food, transportation, and interpersonal safety.
34 | Health Information Exchange | Clinical Care Team | TC1T2 | Is the practice connected with NC HealthConnex? |  | Needed | Tier 2 | NCQA CC21A | https://hiea.nc.gov/providers/about-nc-healthconnex
35 | Health Information Exchange | Clinical Care Team | TC2T2 | Does the clinical team have access to the NC HealthConnex Portal? |  | Needed | Tier 2 |  | https://hiea.nc.gov/services/nc-healthconnex-exchange
36 | Health Information Exchange | Clinical Care Team | TC3T3 | Tier 3 ONLY - Has the practice enrolled in NC* Notify? |  | Needed | Tier 3 | NCQA CC19 | https://hiea.nc.gov/services/ncnotify
37 | Health Information Exchange | Clinical Care Team | TC4 | Tier 3 ONLY - Has the practice determined the workflow for monitoring and integrating ADT Data Feeds in transitional care management? |  | Needed | Tier 3 | NCQA CC14, CC19, CC21A | Requirements for ADT Data feeds is outlined in the AMH Provider Manual and Attestation questions.
38 | Transitional Care Management | Clinical Care Team | TCM1 | Is the practice working on establishing a system for regularly receiving information from hospitals about discharges and ED visits so that follow up can consistently occur. Does the practice have a policy in place that outlines the process? |  | Needed | Tier 2 | NCQA CC14, CC19, CC21A
39 | Transitional Care Management | Clinical Care Team | TCM2 | Does the practice follow up with patients within a designated time interval after an emergency room visit or hospital discharge? Does the practice implement a workflow to utilize TCM codes? |  | Needed | Tier 2 | NCQA CC14, CC19, CC21A
40 | Transitional Care Management | Clinical Care Team | TCM3 | Is the practice consistently following up with patients within a designated time interval after an emergency room visit or hospital discharge. Does the practice consistently utilizes TCM codes? |  | Needed | Tier 3 | NCQA CC14, CC19, CC21A | AMH Tier 3 requirements for Transitional Care Management are outlined in the AMH Provider Manual and Attestation questions.
41 | Patient Value Added Services | Clinical Care Team | V3 | Are clinical providers informed on the new paid behavioral health services for patients through their new PHP? |  | Needed | Tier 2 |  | PHP Provider Manuals contain details for Prior Authorization process and what requires a prior authorization.
42 | Patient Value Added Services | Clinical Care Team | V4 | Are clinical providers informed on the additional paid services for patients through their new PHP? |  | Needed | Tier 2 |  | See PHP Member Handbooks for a listing of all value added services.
43 | Patient Value Added Services | Clinical Care Team | V5 | Is the practice is aware of PHP Value Added Services and will recommend these services to patients in Medicaid Managed Care when clinically necessary? |  | Needed | Tier 2
44 | Patient Value Added Services | Clinical Care Team | V6 | Does the practice understand how the PHP Value Added services have an effect on payments in the Quality Strategy for Medicaid Managed Care. Practice is prepared to utilize or refer patients to these resources with treatment when clinically necessary? |  | Needed | Tier 3
45 | Vaccine Management | Clinical Care Team | VC1 | Does the practice currently offer vaccinations in the office -OR- refers patients to their local health department or another entity for vaccinations and follows-up to ensure that it has been completed? |  | Needed | Tier 2
46 | Vaccine Management | Clinical Care Team | VC2 | Does the practice understand how vaccination status has an effect on the Quality Strategy in Medicaid Managed Care? Is the practice prepared to complete work around closing care gaps for patients in need of vaccinations? |  | Needed | Tier 3
      CLINICAL ADMIN GAP

## TST Tool Dashboard
Standard | Step 1 | Step 2 | Tier 2 Medicaid Managed Care Practice | Tier 3 Medicaid Managed Care Practice
Access- Hours of Operation (A5T2,A6T2,A7T2, A8T3,A9T3) | Practice is open normal business hours and includes phone line for after hours | Practice has the ability to measure wait time for appointment availability and sets appointment availability goals to PHP/DHB Appointment Access & Availability Standards and is working to meet goals. | Practice meets PHP/DHB Appointment Access & Availability Standards. | Practice offers improved access through same day appointments and expanded hours or alternative appointment types (telemedicine).
Needed
Access-After Hours Communication (A1T2,A2T2,A3T2,A4T3) | Practice provides after hours phone line with automated recording and the ability to leave a message. | Practice offers 24 hour access with an after hours on-call phone line that will connect to a clinical representative within 30 minutes. | Practice offers 24 hour access with an after hour on call phone line that will connect to a real person and page on-call provider. | Practice offers 24 hour access with an after hour on call phone line that will connect to a clinical representative or provider on-call.
Needed
Practice Management- PHP Participation | No PHP Contracts have been finalized. Front office staff know which PHPs are in-network with your practice? | PHP contracts have been completed and Practice has access to each in-network PHP Provider Manual for review. Front office staff know which PHPs are in-network with your practice. | Practice has reviewed all PHP Provider Manuals and completed PHP Orientation & Training
Needed
PHP Identification & Onboarding | Front desk staff are trained on identifying each PHP insurance card and understand practice in-network PHP plans. | All contracted PHP insurances are built into the practice management system and available for front desk to use. | Front office staff are trained on how enrollees are assigned to PCPs and understand practice policies for how to assist enrollees in requesting a change in their PCP.
Needed
Front Office-Member Eligibility | Front office staff are trained on how to verify and document insurance information (eligibility, PHP, PCP, etc.) at patient registration. | Front office staff been trained on when or how often to check eligibility for the new PHP plans. If practice has auto verification of eligibility available in practice management system, has this feature been updated to include the new PHPs. | Practice is successful at registering, eligibility checking and submitting claims to new PHP plans. Practice has successfully checked Eligibility on Medicaid Managed Care Plan test patients.
Needed
Billing & Claims Readiness | Are all contracted PHP insurances built into the practice management system? | Have you determined the process for where payments from PHPs will be received for Patient Visits & Services? | Practice has reviewed the process for receiving patient EOBs and is ready to receive payments. | Practice has determined the process for where payments from PHPs will be received for (PMPM Care Management Fee) Care Management Services and Quality Incentive Programs (Performance Incentive Payments).
Needed
Practice Management- Quality Strategy | Practice has understanding of quality reporting and how it relates to Medicaid Managed Care | Practice has knowledge of where to find quality reports both in their EHR and with each in-network PHP | Practice has reviewed each PHP quality standard requirement and is prepared to receive patient quality reports | Practice has determined staff that will receive quality & cost reports from the PHPs and/or CIN. Practice understands role in improving quality and working care gaps.
Needed
Cultural Competency | Practice includes cultural competency training to all staff annually. | Practice includes cultural competency training to all staff annually and incorporates cultural competency in patient communication. | Practice includes cultural competency training to all staff quarterly, incorporates cultural competency in patient communication every day and uses cultural competency language/material when providing written materials to patients.
Needed
Language Line | Practice is aware of PHP language line resources. | Practice uses PHP language line resources when requested by provider during an appointment. | Practice pro-actively includes patient primary language in pre-visit planning to schedule interpreter services during the patient visit.
Needed
Patient Population/Empanelment | Practice currently accepts patients with NC Medicaid and is able to generate reports on current active or attributed Medicaid patients. | Practice is making determinations on Medicaid patient panel size and understands patient attribution in Medicaid Managed Care. Practices communicate to their patients which PHP plans will be in-network. | Practice is able to obtain attributed patient lists from each in-network PHP. Practice has reconciled the list with the practice EHR to determine new attributed patients, incorrect attributed patients and general additonal workload during the first months of Managed Care. Practice has a policy in place to determine the process and frequency of reconciling the panel lists.
Needed
Vaccine Management | Practice currently offers vaccinations in the office -OR- Practice refers patients to their local health department or another entity for vaccinations and follows-up to ensure that it has been completed. |  |  | Practice understands how vaccination status has an effect on the Quality Strategy in Medicaid Managed Care. Practice is prepared to complete work around closing care gaps for patients in need of vaccinations.
Needed
Referral Management | Primary Care Provider takes on referral determination for all referral decisions related to the patient. | Practice understands which PHP plans require prior authorization for referrals to specialists. | Are clinical providers & referral coordinators aware of common referral providers that are in-network with patient plans? | Practice has a process to track referrals to ensure completion and that the consult note has been received and reviewed by the ordering provider.
Needed
Patient Value Added Services | Clinical providers are informed on the additional paid services for patients through their new PHP Plans. | Clinical providers are informed on the new paid behavioral health services for patients through their new PHP Plans. | The practice is aware of PHP Value Added Services and will recommend these services to patients in Medicaid Managed Care when clinically necessary. | Practice understands how the PHP Value Added services have an effect on payments in the Quality Strategy for Medicaid Managed Care. Practice is prepared to utilize or refer patients to these resources with treatment when clinically necessary.
Needed
Patient Documentation Requirements | Adults Only -Practice has a process for asking patients about Advance Directives or a Living Will and provides resources to patients on request. |  |  | Practice or contracted organization is able to perform and document a Comprehensive Assessment as part of a clinician visit, or separately by a team led by a clinician with a minimum credential of RN or LCSW. (attach link to understanding Comp Assess)
Needed
Health Information Exchange | The practice is connected to NC HealthConnex |  | The clinical team members have access to the NC HealthConnex Portal. | Practice has determined the workflow for monitoring and integrating ADT Data Feeds for patient transitions of care. OR- Practice has enrolled in NC* Notify to use for ADT Data Feeds in patient transitions of care.
Needed
Transitional Care Management | Practice is working on establishing a system for regularly receiving information from hospitals about discharges and ED visits so that follow up can consistently occur. |  | Practice is performs follow up with patients within a designated time interval after an emergency room visit or hospital discharge but is not yet consistently accomplishing this goal. Practice is beginning to implement a workflow to utilize TCM codes | Practice is consistently following up with patients within a designated time interval after an emergency room visit or hospital discharge. Practice consistently utilizes TCM codes
Needed
Social Determinants of Health | The clinical team has completed training on understanding Social Determinants of Health as it relates to Medicaid Managed Care. | Practice has knowledge of area community resources to assist patients with social determinates. | Practice has access to and utilizes area community resources to assist patients with social determinates of health. Or Practice is enrolled and utilizes NCCARE360 for meeting patient needs. | Practice had determined who will receive "Care Needs Screening" reports and how those are going to be documented in the EHR and communicated to the PCP provider.
Needed
Care Management Process | Practice has basic knowledge of care management and how it relates to Medicaid Managed Care | Practice has determined a process for patient referral to care management services. Practice includes communication workflow between the PCP and the assigned Care Manager as part of process. | Practice uses formalized workflow for referring patients to PHP care management and tracks referrals to ensure patients are using the service. | Practice has policy in place that outlines care management process, defines the process and frequency of enrollment review and includes procedures on how Care Plans provided electronically to primary care provider within 30 days of receiving the Comprehensive Medical Assessment and after each appointment thereafter. Practice uses CIN or Care Management organization to provide care management services to patients internally in their practice OR Practice has a Care Manager on site to provide services to enrolled patients. Care Plans are documented in the practice EHR and reviewed/updated at least annually with the patient and primary care provider.
Needed
Care Management Patient Enrollment | Practice begins to determined enrollment criteria for referral to care management. | Practice receives encounter data/cost reports from PHP on high-risk patients eligible for care management referral. | Practice includes high-risk reports, HCC scores, Co-Morbidity Diagnosis and/or prevalence of Social Determinates in care management referral criteria. | Practice has a policy for Care Management Enrollment. Practice uses at minimum PHP Risk Scoring Reports for Care Management enrollment criteria to stratify patients by risk levels and incorporates risk reports in all aspects of patient care. Policy includes frequency of risk scoring review and validation. Practice has designated staff member to receive and compile PHP risk scoring results.
Needed
  TST TOOL DASHBOARD

## Attestation
Practice Name: | ACME Happy Practice
Advanced Medical Home Tier 3 Attestation Requirements
Risk Stratification: Tier 3 AMHs must be able to risk stratify all empaneled patients.
Requirement | Rationale | Suggested Action | Answer YES/NO (Must Be Yes) | Notes
Can your practice ensure that assignment lists transmitted to the practice by each PHP are reconciled with the practice’s panel list and up-to-date in the clinical system of record? | Updated Policy on Risk Stratification: https://files.nc.gov/ncdma/AMH_Risk-Stratification-Guidance_8-16-2019.pdf. There is no set minimum interval at which practices should perform this review but practices should develop a process to ensure that it is done when clinically appropriate. The clinical system of record is an electronic health record or equivalent. | Complete practice process/policy document that defines responsible roles and outlines the process.
Does your practice use a consistent method to assign and adjust risk status for each assigned patient? | Practices are not required to purchase a risk stratification tool; risk stratification by a CIN/partner or system would meet this requirement or application of clinical judgment to risk scores received from the PHP or another source will suffice. | Complete practice process/policy document that outlines who is responsible for completing risk stratification.
Can your practice use a consistent method to combine risk scoring information received from PHPs with clinical information to score and stratify the patient panel?
To the greatest extent possible, can your practice ensure that the method is consistent with the Department’s program Policy of identifying “priority populations” for care management? | Not all care team members need to be able to perform risk stratification (for example, risk stratification will most likely be done at the CIN/partner level, or may be performed exclusively by physicians if done independently at the practice level), but all team members should follow stratification-based protocols (as appropriate) once a risk level has been assigned. | Complete practice process/policy document that outlines: -how risk status is assigned and documented for each patient -care team training of risk management methodology
Can your practice ensure that the whole care team understands the basis of the practice’s risk scoring methodology (even if this involves only clinician judgment at the practice-level) and that the methodology is applied consistently?
Can your practice define the process and frequency of risk score review and validation? | Practices should be prepared to describe these elements for PHPs. | Complete practice process/policy document that outlines the frequency of risk score review and validation (Appendix A: Example practice risk assignment process)
Advanced Medical Home Tier 3 Attestation Requirements
Care Management to High-Need Patients: Tier 3 AMHs must provide care management to high-need patients.
Requirement | Rationale | Suggested Action | Answer YES/NO (Must Be Yes) | Notes
Using the practice’s risk stratification method, can your practice identify patients who may benefit from care management? | Practices should use their risk stratification method to inform decisions about which patients would benefit from care management, but care management designations need not precisely mirror risk stratification levels.
Can your practice perform a Comprehensive Assessment (as defined below) on each patient identified as a priority for care management to determine care needs? The Comprehensive Assessment can be performed as part of a clinician visit, or separately by a team led by a clinician with a minimum credential of RN or LCSW. The Comprehensive Assessment must include at a minimum: · Patient’s immediate care needs and current services; · Other State or local services currently used; · Physical and dental health conditions; · Current and past behavioral and mental health and substance use status and/or disorders; · Physical, intellectual developmental disabilities; · Medications; · Priority domains of social determinants of health (housing, food, transportation, and interpersonal safety); · Available informal, caregiver, or social supports, including peer supports. · At PHP's option and for adults only, exposure to adverse childhood experiences (ACEs) or other trauma | In preparation for the assessment, care team members may consolidate information from a variety of sources, and must review the Initial Care Needs Screening performed by the PHP (if available). The clinician performing the assessment should confirm the information with the enrollee. After its completion, the Comprehensive Assessment should be reviewed by the care team members. The assessment should go beyond a review of diagnoses listed in the enrollee's claims history and include a discussion of current symptoms and needs, including those that may not have been documented previously. The section of the assessment reviewing behavioral and mental health may include brief screening tools such as the PHQ-2 or GAD-7 scale, but these are not required. The enrollee may be referred for formal diagnostic evaluation. The practice or CIN/partners administering the Comprehensive Assessment should develop a protocol for situations when an enrollee discloses information during the Assessment indicating an immediate risk to self or others. The review of medications should include a medication reconciliation on the first Comprehensive Assessment, as well as on subsequent Assessments if the enrollee has not had a recent medication reconciliation related to a care transition or for another reason. The medication reconciliation should be performed by an individual with appropriate clinical training. | Process/Policy outlining: -what the practice's Comprehensive Assessment includes - what assessment tools will be used and when - when to refer enrollee for formal diagnostic evaluation - protocol for when an enrollee discloses information indicating an immediate risk to self or others
Does your practice have North Carolina licensed, trained staff organized at the practice level (or at the CIN/partner level but assigned to specific practices) whose job responsibilities encompass care management and who work closely with clinicians in a team-based approach to care for high-need patients? | Care managers must be assigned to the practice, but need not be physically embedded at the practice location.
For each high-need patient, can your practice assign a care manager who is accountable for active, ongoing care management that goes beyond office-based clinical diagnosis and treatment and who has the minimum credentials of RN or LCSW? (See supplemental question 6 to provide further information.) | An enrollee may decline to engage in care management, but the practice or CIN/partners should still assign a care manager and review utilization and other available data in order to inform interactions between the enrollee and their clinician during routine visits.
Documented Care Plan: For each high-need patient receiving care management, Tier 3 AMHs must use a documented Care Plan.
Requirement | Rationale | Suggested Action | Answer YES/NO (Must Be Yes) | Notes
Can your practice develop the Care Plan within 30 days of Comprehensive Assessment or sooner if feasible while ensuring that needed treatment is not delayed by the development of the Care Plan? | 30 days is the maximum interval for developing a Care Plan. If there are clinical benefits to developing a Care Plan more quickly, practices should do so whenever feasible.
Can your practice develop the Care Plan so that it is individualized and person-centered, using a collaborative approach including patient and family participation where possible? | Practice may identify their own definitions of ‘individualized’, ‘person-centered’ and ‘collaborative’, but should be able to describe how their care planning process demonstrates these attributes.
Can your practice incorporate findings from the PHP Care Needs Screening/risk scoring, practice-based risk stratification and Comprehensive Assessment with clinical knowledge of the patient into the Care Plan? Can your practice include, at a minimum, the following elements in the Care Plan?: · Measurable patient (or patient and caregiver) goals · Medical needs including any behavioral health needs; · Interventions; · Intended outcomes; and · Social, educational, and other services needed by the patient. | Intended outcomes can be understood as clinical steps identified by the care team that will lead to the enrollee/caregiver-defined goal. For example, the enrollee may set a goal of no longer needing frequent finger sticks and injected insulin. The care team may develop an intended clinical outcome that represents the level of glycemic control at which the enrollee could attempt a trial of oral hypoglycemic, and a second intended clinical outcome that represents the level of control on oral hypoglycemic that would allow the enrollee to continue with the regimen.
Does your practice have a process to update each Care Plan as beneficiary needs change and/or to address gaps in care; including, at a minimum, review and revision upon re-assessment? | There is no set minimum interval at which practices should perform this review but practices should develop a process to ensure that it is done when clinically appropriate.
Does your practice have a process to document and store each Care Plan in the clinical system of record? | The clinical system of record may include an electronic health record.
Can your practice periodically evaluate the care management services provided to high-risk, high-need patients by the practice to ensure that services are meeting the needs of empaneled patients, and refine the care management services as necessary? | There is no set minimum interval at which practices should perform this review but practices should develop a process to ensure that it is done when clinically appropriate.
Advanced Medical Home Tier 3 Attestation Requirements
Documented Care Plan: For each high-need patient receiving care management, Tier 3 AMHs must use a documented Care Plan.
Requirement | Rationale | Suggested Action | Answer YES/NO (Must Be Yes) | Notes
Can your practice track empaneled patients’ utilization in other venues covering all or nearly all hospitals and related facilities in their catchment area, including local emergency departments (EDs) and hospitals, through active access to an admissions, discharge, and transfer (ADT) data feed that correctly identifies when empaneled patients are admitted, discharged, or transferred to/from an emergency department or hospital in real time or near real time? | While not required, practices are also encouraged to develop systems to ingest ADT information into their electronic health records or care management systems so this information is readily available to members of the care team on the next (and future) office visit(s) .
Can your practice or CIN implement a systematic, clinically appropriate care management process for responding to certain high-risk ADT alerts (indicated below)? · Real time (minutes/hours) response to outreach from EDs relating to patient care or admission/discharge decisions, for example arranging rapid follow up after an ED visit to avoid an admission; · Same-day or next-day outreach for designated high-risk subsets of the population to inform clinical care, such as beneficiaries with special health care needs admitted to the hospital; · Within a several-day period to address outpatient needs or prevent future problems for high risk patients who have been discharged from a hospital or ED (e.g., to assist with scheduling appropriate follow-up visits or medication reconciliations post discharge) | Practices (directly or via CIN/partners) are not required to respond to all ADT alerts in these categories, but they are required to have a process in place to determine which notifications merit a response and to ensure that the response occurs. For example, such a process could designate certain ED visits as meriting follow-up based on the concerning nature of the patient’s complaint (suggesting the patient may require further medical intervention) or the timing of the ED visit during regular clinic hours (suggesting that the practice should reach out to the patient to understand why he or she was not seen at the primary care site). The process should be specific enough with regard to the designation of ADT alerts as requiring or not requiring follow-up; the interval within which follow-up should occur; and the documentation that follow-up took place that an external observer could easily determine whether the process is being followed. | Process/Policy outlining: - definition of ED visits that merit follow-up from the practice -the interval within which follow-up should occur -how the follow-up will be documented
Transitional Care Management: Tier 3 AMHs must be able to provide short-term, transitional care management along with medication reconciliation to all empaneled patients who have an emergency department (ED) visit or hospital admission/discharge/transfer and who are at risk of readmissions and other poor outcomes.
Requirement | Rationale | Suggested Action | Answer YES/NO (Must Be Yes) | Notes
Does your practice have a methodology or system for identifying patients in transition who are at risk of readmissions and other poor outcomes that considers all of the following?: · Frequency, duration and acuity of inpatient, SNF and LTSS admissions or ED visits · Discharges from inpatient behavioral health services, facility-based crisis services, non-hospital medical detoxification, medically supervised or alcohol drug abuse treatment center; · NICU discharges; · Clinical complexity, severity of condition, medications, risk score
For each patient in transition identified as high risk for admission or other poor outcome with transitional care needs, can your practice assign a care manager who is accountable for transitional care management that goes beyond office-based clinical diagnosis and treatment and who has the minimum credentials of RN or LCSW? | An enrollee may decline to engage in care management, but the practice or CIN should still assign a care manager and review utilization and other available data in order to inform interactions between the enrollee and their clinician during the transition period. | Ensure practice has access to a care manager who has minimal credentials of RN or LCSW.
Does your practice include the following elements in transitional care management? · Ensuring that a care manager is assigned to manage the transition · Facilitating clinical handoffs; · Obtaining a copy of the discharge plan/summary; · Conducting medication reconciliation; · Following-up by the assigned care manager rapidly following discharge; · Ensuring that a follow-up outpatient, home visit or face to face encounter occurs · Developing a protocol for determining the appropriate timing and format of such outreach | The AMH practice is not required to ensure that follow-up visits occur within a specific time window because enrollees’ needs may vary. However, the practice must have a process for determining a clinically appropriate follow-up interval for each enrollee that is specific enough with regard to the interval within which follow-up should occur and the documentation that follow-up took place so that an external observer could easily determine whether the process is being followed.
Claims Data Feeds: Tier 3 AMHs must use electronic data to promote care management.
Requirement | Rationale | Suggested Action | Answer YES/NO (Must Be Yes) | Notes
Can your practice receive claims data feeds (directly or via a CIN/partner) and meet Department-designated security standards for their storage and use?
  ATTESTATION

## Project Plan
  PROJECT PLAN

## Yr 1 Quality Measures
AMH Finaly Quality Measures were discussed during the Advanced Medical Home Webinar on November 5, 2020 as a part of the Medicaid Managed Care Fireside Chat Webinar Series. Pictured here is slide 20. You can access future and past recordings of the Fireside Chat on the NC AHEC Medicaid Managed Care Page link provided below.
  YEAR 1 QUALITY MEASURES
ncahec.net/medicaid-managed-care

## Sheet2 (hidden)
| Practice | Ready | YES
| CIN | In Progress | NO
| Unsure | Needed
E3 Lookup
NeededNeeded | Under the Access and Availability Standards, a practice must be able to see a patient with urgent needs within 24 hours. Having same day open appointments or an alliterative appointment type such as telemedicine can help to meet this requirement. When the front office chooses the insurance under registration, they may find several of the same named plans that are commercial. Consider naming these insurances in the system so that they are easily recognizable. One way to do this is to put NC Medicaid at the front or end of the insurance name.
Ready