## Sheet1 (hidden)
Status
needed
in-progress
ready

## Cover Letter
CHW Clinical Integration Cover Letter
Purpose
The purpose of this toolkit is to provide healthcare practices with information and guidance for integrating Community Health Workers (CHWs) into their practice settings. Before getting started, we recommend you review the CHW 101 Tab to learn more about the CHW profession and review the links provided for additional information to help you with your planning. The Overview Tab provides information on how to use the toolkit.
Objectives
The objective of this toolkit is to ensure Medicaid participating primary healthcare practices and other organizations have the information needed to effectively integrate CHW services into their clinical and administrative workflow.
Additional Recommendations
Inherent in the roles of the CHW workforce is a recognition of social drivers of health which disproportionally impact low income communities. As you begin the process of understanding how CHWs can fit into your practice setting and support your patient population, we invite you to also explore ways you can work with employees across your organization to increase awareness and understanding of these social barriers.
Practice information
PRACTICE NAME:
ADDRESS:
CONTACT NAME:
EMAIL:
AMH TIER:
CIN:
Practice Support Coach(s):
Start Date: | Start Date:
Acknowledgement
The CHW Clinical Integration Tool was developed for NC Medicaid by NC AHEC along with partners listed below and may be copied, without permission, in its entirety.
Individuals serving on the CHW Clinical Integration Workgroup: (in alphabetical order)
Abdul Hafeedh bin Abdullah, CHASM |  | Julie Shelton, MAHEC | Shannon Cambra, Area L AHEC
Erica Hall, NCCHCA |  | Katherine Andersen, SEAHEC | Shaunessy Lofton, Partner in Health
Evan Richardson, NC AHEC |  | Monique Mackey, Area L AHEC | Kaitlyn Wease, NC AHEC
Je'Wana Grier-McEachin, ABIPA |  | Robert Shapiro, SEAHEC | Sherrie Wise Thomas, Wake Forest Health
Jess Rothenhoefer, NC AHEC |  | Rumana Rabbani, CHASM | Teresa Wiley, Community Care of North Carolina
Josie Lane-Kuzniar, NCCHCA |  | Sallie Allgood, Durham VHA, Duke University | Yvette Singleton, MAHEC and ABIPA
Development of a companion document and case reports are supported by a Rita and Alex Hillman Foundation Hillman Scholar in Nursing Innovation Small Grant awarded to Sallie Allgood.

## 1. CHW 101
CHW 101
Purpose | The purpose of the CHW 101 Tab is to provide key background information about Community Health Workers, their role, and the potential impact of CHWs and CHW programs. A common barrier to successful integration of CHWs into healthcare settings is a misunderstanding of who CHWs are, their scope of practice, and how they can best contribute to improving individual and community health outcomes.
Instructions | We recommend practice teams engaging in integrating or optimizing CHW programs to review this tab in its entirety as an important first step.
Who is a Community Health Worker?
“A frontline public health worker who is a trusted member of and/or has an unusually close understanding of the community served. This trusting relationship enables the worker to serve as a liaison/link/intermediary between health/social services and the community to facilitate access to services and improve the quality and cultural competence of service delivery. A community health worker also builds individual and community capacity by increasing health knowledge and self-sufficiency through a range of activities such as outreach, community education, informal counseling, social support and advocacy.” -- American Public Health Association Community Health Worker Section, 2010.
Resources
• Video from national CHW Core Consensus (C3) Project provides additional information about CHWs.
• One of the most important things that CHWs do is to lead with empathy and offer compassion rooted in relationship.
• Read these CHW stories from the Healthy Living through Environmental, Policy, and Improved Clinical Care (EPICC) Program, Utah, website.
CHW Job Titles
There are more than 150 job titles used for Community Health Workers across the country. Below are a few of them:
Asthma Outreach Worker Addiction Treatment Specialist Bilingual Family Advocate Care Coordinator Care Navigator Certified Application Assistant Close-to-Community Providers Community Aide Community Care Worker Community Connector Community Health Ambassador Community Health Coordinator |  | Community Health Navigator Community Health Representative Community Liaison Community-Clinical Linkage Specialist Cultural Case Manager Cultural Mediator Diabetes Navigator Enrollment Worker Family Advocate Family Support Worker Frontline Health Worker |  | Health Communicator Health Extension Worker Health Facilitator Health Information Specialist HIV Peer Advocate Home Visitor Homeless Advocate Lay Health Advisor Medical Representative Mental Health Worker Multicultural Health Brokers Neighborhood Health Advocate | Outreach Coordinator Parent Liaison Peer Advocate Peer Leader Promotora de Salud Social Determinant of Health Specialist Street Workers Wellness Ambassadors Youth Worker
CHW Roles and Responsibilities:
Role 1: Cultural Mediation |  |  | Lived experience gives CHWs first-hand knowledge of the communities in which they work and serve. This uniquely qualifies CHWs to act as bridges between individuals, communities, and health and social service systems.
Role 2: Culturally Appropriate Health Education |  |  | CHWs are uniquely qualified to provide health education and information in a way that matches the cultural and linguistic needs of individuals and communities, thus helping individuals understand, manage, and optimize their health.
Role 3: Care Coordination, Care Management, and System Navigation |  |  | CHWs link individuals and families to resources to address the social drivers that impact health and wellness. CHWs also follow up to ensure referrals result in needed support. This role makes CHWs a vital voice for healthcare providers and systems seeking to understand community assets and challenges.
Role 4: Providing Coaching and Social Support |  |  | CHWs provide coaching, support, and motivation to individuals and/or groups, for the adoption of healthier lifestyles and understanding the importance of engaging in one’s own care; both are key strategies for building capacity to manage health conditions and prevent disease.
Role 5: Advocating for Individuals and Communities |  |  | CHW advocacy takes on many forms and is tailored to the perspectives and needs of their communities. CHWs advocate: 1) with and on the behalf of individuals and communities to ensure community members are treated respectfully and given access to services and resources needed to live healthy lives. 2) on services provided and the service experience for community members who access and utilize the services. 3) for engagement and mobilization to improve health and well-being (e.g., affordable housing, access to healthy food, access to transportation, access to healthcare, violence prevention, etc.).
Role 6: Building Individual and Community Capacity |  |  | CHWs support clients and community members to develop the necessary skills and confidence to advocate for their own health and well-being.
Role 7: Provide Direct Service |  |  | CHWs work with individuals at their homes and/or within the community to provide basic health screening services (e.g., height, weight, blood pressure, basic first aid, depression screening, and social determinants of health screening) and address individual needs that impact their health (e.g., deliver food boxes, provide transportation). CHWs can also provide Care Needs Screening as part of the Care Team.
Role 8: Implementing Individual and Community Assessments |  |  | CHWs can perform individual and community assessments, such as home safety and environmental assessments, community health assessment, and mapping community assets. They are vital partners for health care and public health organizations and systems seeking to deepen community engagement and strengthen community health improvement programs.
Role 9: Conducting Outreach |  |  | CHW outreach can take many forms: 1) Engage individuals in services and programs through outreach and recruitment conducted during community events, home visits, telephone calls, and texts. 2) Follow up with individuals and families after service encounters to support continued engagement in care and recommendations, including attending healthcare appointments. 3) Contribute to outreach at a community and system level by making presentations to local agencies, community groups, community/county boards, and other arenas.
Role 10: Participating in Evaluation and Research |  |  | CHWs contribute a vital perspective and knowledge base to the design and implementation of program evaluation. CHWs bring an understanding of urgent issues for the community; they can engage community members as partners through authentic community-based research and they can advocate for stakeholders to take actions based on findings. The impact of the services they provide makes CHWs vital partners in the design and implementation of authentic community-based participatory research.
What Impacts do CHWs and CHW Programs Make?
CHW programs impact the triple aim: population health outcomes, service experience and healthcare costs. 1 Specifically, CHWs are an effective workforce for improving preventive care, chronic disease management, and mental health care among all populations. CHWs also improve service experience ratings for primary care among individuals receiving services. CHW interventions reduce Emergency Department utilization, re-hospitalization rates, and contribute to significant healthcare savings.2 One randomized controlled trial of CHW interventions demonstrated an average savings of $2.47 for every $1 Medicaid dollar spent in one fiscal year. 3 CHWs also improve access to care in rural and low-income communities.4
1. Massachusetts Department of Public Health. Achieving the Triple Aim: Success with Community Health Workers. Massachusetts Department of Public Health; 2015:12. Accessed November 9, 2021. https://www.mass.gov/doc/achieving-the-triple-aim-success-with-community-health-workers-0/download 2. Association of State and Territorial Health Officials (ASTHO), National Association of Community Health Workers (NACHW). Community Health Workers: Evidence of Their Effectiveness. ASTHO Accessed October 29, 2021. https://www.astho.org/Programs/Clinical-to-Community-Connections/Documents/CHW-Evidence-of-Effectiveness/ 3. Kangovi S, Nandita M, Grande D, Long J, Asch D. Evidence-Based Community Health Worker Program Addresses Unmet Social Needs And Generates Positive Return On Investment. Health Affairs. 2020;39(2). doi:10.1377/hlthaff.2019.00981 4. Rural Health Information Hub (RHIhub). Advantages of Community Health Workers in Rural Health Settings. Accessed October 29, 2021. https://www.ruralhealthinfo.org/toolkits/community-health-workers/1/advantages
What Are Key Elements for Successful CHW Program Implementation?
Hiring: |  |  | A clear vision for the CHW program, CHW's role, AND a realistic implementation plan and timeline.
Training: |  |  | Invest in onboarding staff, initial training, and have a plan and workflow in place for evaluating skills and ongoing training needs.
Supervision: |  |  | Effective CHW supervision and mentoring is vital to CHWs and CHW program success. CHW supervisors should ideally be experienced CHWs or have a good understanding of the CHW role. Specific training for CHW supervisors is available and listed in the "Implementation Resources Tab".
Respect for CHW Culture and Roles: |  |  | Respect for CHWs begins with understanding their role and impact. Healthcare organizations that have a commitment to advancing health for all and learning from the expertise CHWs bring to the table are more likely to be successful in sustaining effective CHW programs. It is important that leaders and respected champions are able to speak to the role and benefits of CHWs and empower CHWs to share data and stories regularly.
Program Evaluation: |  |  | The structure of a CHW program (hiring, training, supervision) that incorporates a methodical program plan, and measurements of impact will create a powerful recipe for improving health outcomes and healthcare costs. It is important to track both process and outcome measures.
This section developed in consultation with the following references: 1. Brooks BA, Davis S, Frank-Lightfoot L, Kulbok PA, Poree S, Sgarlata L. Building A Community Health Worker Program: The Key to Better Care, Better Outcomes, & Lower Costs. CommunityHealth Works; 2018:57. Accessed October 29, 2021. https://www.aha.org/system/files/2018-10/2018-chw-program-manual-toolkit.pdf 2. 2. Gutierrez KA, Campbell. Best Practice Guidelines for Implementing and Evaluating Community Health Worker Programs in Health Care Settings. Sinai Urban Health Institute; 2014:151. Accessed October 29, 2021. https://chwcentral.org/wp-content/uploads/2014/01/CHW-BPG-for-CHW-programs-in-health-care-settings.pdf

## 2. Overview
Toolkit Overview
Using this toolkit
Following the steps outlined below, along with the tabs of this toolkit will guide you through the process of preparing, planning, and implementing CHWs into your practice. The process we recommend is based on evidence based approaches to effective implementation and change.
Each tab walks you through a different step in the planning process and/or provides vital resources. 1) CHW 101 2) Overview - You are HERE! 3) Gap Analysis 4) Key Drivers of Impact 5) Project Management Plan 6) Evaluation and Sustainability 7) Implementation Resources 8) CHW FAQs Each tab begins with information about its purpose and instructions.
Step 1: Form a Team
A team approach supports successful CHW program development and implementation. An ideal team includes representatives from stakeholder groups who will be impacted by the program and/or whose engagement can help build momentum for change and implementation. Examples include providers, administrative leadership, clinical support staff, care management staff, patients, community-based organizations, and CHWs. IF YOUR PRACTICE DOES NOT HAVE AN EXISTING RELATIONSHIP WITH LOCAL COMMUNITY-BASED ORGANIZATIONS OR CHWS, SEE STEP 3.
Step 2: Learn about CHWs
Healthcare teams commonly misunderstand the role, scope, and full potential of CHWs and, as a result, limit the effectiveness and impact of CHWs and CHW programs. The CHW 101 Tab provides foundational background information to ensure all on the planning team understand the full potential of CHWs and CHW programs. It is important that all members of the team have a foundational knowledge so they can speak to their peers accurately about the role, scope, and impact of CHWs.
Step 3: Build Authentic Community Relationships
CHW services and programs intentionally focus on supporting health for all. It is vital that practices allow themselves to be guided by partnership with community members, CHWs and/or community-based organizations who are trusted by their patients. Some practices may need to start with building authentic relationships with community partners on their journey towards integrating CHWs. Authentic community engagement, when done well, takes time. It is rewarding work that can bring forth a number of possibilities for practices and community partners.
Step 4: Identify Community and Practice Level Opportunities to Advance Health for All
Social drivers have a significant impact on a person's health. The conditions in which people are born, grow, work, and age account for nearly 80% of what impacts the length and quality of a person's life. CHW services and programs provide practices an opportunity to address these social drivers of health in a meaningful way. We recommend practices intentionally design CHW services and programs to ensure they make an impact on the health outcomes, experience, and cost of care for individuals and families served by the practice, as well as, be part of a larger effort to improve overall health and wellbeing in the community.
Step 5: Establish Overall Desired Result/Impact
Begin planning with the end in mind. Using this approach will provide clarity and motivation for all engaged in the work, as well as, increasing efficiency, effectiveness, and success. This step will guide the team to develop specific high-level improvement goals (a.k.a. AIM statements) that will guide implementation. Goals will be set for both population or community level result/s, as well as, practice level impact/s.
Step 6: Identify Key Drivers of Impact
A Driver Diagram helps translate a high-level improvement goal or AIM into a logical set of related goals and sub-projects. The tool organizes change ideas around the question “What changes can we make that will result in achieving our AIM?” The components include the overall AIMs, the primary drivers (factors that have a direct impact on achieving the AIMS), and the secondary drivers (clearly defined actions that lead to creating the conditions described in the primary drivers). The resulting graphic can be updated as needed based on the learnings from tests of change and implementation. It can also be used to communicate to others the overall picture of CHW program development and implementation.
Step 7: Identify Measures of Success and Prepare for Ongoing Evaluation
It is important to establish a clear understanding of how you plan to measure success and the potential unintended outcomes of your program, so you can monitor how you are doing as you proceed through initial pilot testing to spread ongoing optimization. Keeping it simple is a good approach - you want to make sure that you focus on data that is meaningful and relatively easy to collect and report. Key questions you will want to ask yourself as you determine how you measure success include: “How much did we do? How well did we do it? Is anyone better off?". Regularly reviewing data as a team and adjusting as needed based on learning is key to success. Intentionally starting small, testing out new ideas, and learning what works and what needs to be tweaked lowers the risk of "failure". Rather than "failing" you are learning. It is important to incorporate into your CHW program plan and timeline, the necessary time to test out new aspects of the program. Examples include a) Start with 1-2 providers working with the CHW and limiting the total number of individuals referred to the CHW for a short period of time; b) Test an approach to weekly CHW supervision meetings for a short period of time to learn what works and what to tweak as you are beginning to implement this aspect of the program; c) Test a new community resource with a few individuals before adding it to the list of vetted resources. The toolkit provides your team with an overall evaluation plan and resources to guide you in the process.
Step 8: Begin Site Preparation
Implementation often involves a lot of detailed work behind the scenes, such as developing a business plan; recruiting, hiring or subcontracting, and onboarding CHWs; establishing workflows and documentation requirements for CHW services; and ensuring CHWs have appropriate training, supervision, and resources to perform their job functions/role. It is important to account for the time it will take to prepare for and complete this detailed wok as part of the overall project timeline.
Step 9: Build Awareness and Momentum for the CHW Program
Organizational change is a team sport. The more people who are engaged and contribute to the new initiative, the more supportive they are likely to be, lending to less resistance to the implementation. It is important to be intentional with communications regarding the implementation, such as, raising awareness of upcoming changes through trainings, conducting ongoing program evaluations/sharing those results, and the growth of the program. It is common to encounter a wide range of feedback from customers, employees, and partners. This feedback is often extremely useful. Responding to it can help build support for the new initiative. Organizations that intentionally build in time to raise awareness, listen, respond to feedback, and engage individuals who show interest and passion for the work have increased success in new initiatives.
Step 10: Plan for Sustainability and Growth of the CHW Program
Successful expansion and spread of a new initiative are important aspects of the implementation process. Having a structured plan to support program growth and sustainability is essential and will ensure ongoing learning and long-term success of the program.

## 3. Gap Analysis
Gap Analysis
| Purpose | The purpose of the gap analysis is to gain a better understanding of the current state of your setting including community, clinic, resources, limitations, and needs. Using information about the current state will help you create a plan to reach the intended outcomes. To complete the gap analysis, follow the steps below to: (1) better understand the community served and identify opportunities for your organization to contribute to better health, including quality of life, in the community, (2) identify if CHW services are an appropriate intervention for community health improvement, (3) understand the characteristics of your practice and team member's understanding of CHWs, (4) engage CHWs and key stakeholders to develop the CHW program, goals, and objectives.
| Instructions | Complete the gap analysis tool with your practice support coach and current team. For each recommendation item, mark the status as "needed", "in-progress", or "ready". In the "Actions Needed" column, enter the steps you need to take to achieve a "ready" status, as well as the person responsible and the due date. This will auto-populate into your Project Management Plan Tab. Use the tool to update your progress as you move from "needed" to "in progress" to "ready". Assess actions required and review your status on a regular basis.
This tab developed in consultation with the following reference: 1. Centers for Disease Control and Prevention. Including Community Health Workers in Health Care Settings: A Checklist for Public Health Practitioners. Version 1.0. Centers for Disease Control and Prevention; 2019:3. Accessed November 18, 2021. https://www.cdc.gov/dhdsp/pubs/docs/CHW_Integration_Checklist.pdf
Planning CHW Integration in Your Practice: Assessment and Goal Setting
Step 1: Form a Team
Goal: To promote the best practice of including vital perspectives in the planning and implementation process. A well-functioning team should consist of members who are committed and united to the project/work. *Please note: The light-blue boxes contain information that will be automatically copied to your Project Management Plan Tab. Enter the final actions needed in these boxes once the status is marked "Ready".
| Recommendations |  | Status | Actions Needed | Person Responsible | Due Date
| Identify a planning group leader. |  | needed
| Begin by reviewing the Key Driver of Impact Tab to focus on the overall practice level aim, key drivers, and secondary drivers. |  | needed
| Identify community partners and community members, including patients, to be part of your program planning. If you do not have existing relationships - focus on Step 3 below. |  | needed
| Identify members of the practice across all departments and/or areas impacted by this change. |  | needed
| Identify a regularly scheduled meeting at a time that allows all team members to attend. |  | needed
| Identify time for team members, outside of the meeting times, to work on action items. |  | needed
| Create written team charter outlining team member roles, meeting times, and the purpose of the team. |  | needed
Step 2: Learn about CHWs
Goal: To ensure all staff involved in the CHW implementation/program and workflow have a fundamental understanding of the CHW role to ensure they are an accurate source of information regarding CHWs for others in the practice that are impacted by the work.
| Recommendations |  | Status | Actions Needed | Person Responsible | Due Date
| Understand CHWs’ potential roles and contributions to patient outcomes, as well as their core competencies (knowledge, skills and abilities). |  | needed
| Identify Federal and North Carolina laws and policies influencing CHW integration in health care settings (e.g. CHW core competencies, scope of practice, certification, financing, HIPAA). |  | needed
Step 3: Build Authentic Community Partnerships
Goal: To build partnerships with CHWs, Community Based Organization's (CBOs) CHW service providers, and other partners that can participate in the planning, design, promotion, and implementation of the CHW program. This may also include a CBO CHW service provider that the practice will sub-contract with as a CHW vendor.
| Recommendations |  | Status | Actions Needed | Person Responsible | Due Date
| Identify internal and external stakeholders who will be essential in your CHW program (e.g. CHWs, community partners, program participants, health care managers). |  | needed
| Identify the roles each stakeholder will have within your CHW program. Consider sub-contracting directly with a CBO CHW service provider as a strategy. |  | needed
| Identify ways in which you will engage key stakeholders initially and on a continuous basis (e.g. CHW advisory groups, town hall meetings, in-person briefings, newsletter). |  | needed
| Identify and use approaches to gain input from all community partners when developing program goals and objectives. |  | needed
Step 4: Identify Community and Practice Level Opportunities to Advance Health for All
Goal: To gain a better understanding of your local community and practice populations and then identify (1) opportunities to contribute to larger community health results and (2) potential practice specific opportunities for CHW program impact that align with potential community health goals.
| Recommendations |  | Status | Actions Needed | Person Responsible | Due Date
| Understand who is in your community, by identifying the following: population demographics, social landscape (income/poverty, education, health insurance), languages spoken, culture, life experiences, economics and technology differences across your community. |  | needed
| Understand the population served by your practice by identifying the following: population demographics, social landscape (income/poverty, education, health insurance), languages spoken, culture, life experiences, economics and technology differences across your community. |  | needed
| Work with your expanded team, including patients and/or community partners, to identify several community-level and related practice-level improvement opportunities for CHW services to address. |  | needed
| Identify which of the community and practice opportunities are priorities and can be effectively addressed by CHWs. |  | needed
Step 5: Establish Overall Desired Result/Impact
Goal: To establish one specific community health improvement result (AIM) and practice level impact (AIM) that will contribute to the desired result. *Please note: as you complete this section of the gap analysis, the Key Drivers of Impact Tab will be automatically updated with what is entered in the light-blue boxes. NOTE: These should be developed in collaboration with stakeholders, CHWs, community members, and members of the health care team.
| Recommendations |  | Status | Add Aims Below | Person Responsible | Due Date
| Identify the overall community health improvement result (AIM) that your practice will contribute to as one of the many partners in your community working together collectively. Include community partners, stakeholders, and/or patients as part of this work. |  | needed
| Identify the overall practice level impact (AIM) to focus on, using evidence-based CHW strategies and interventions. Identify the specific population(s), as well as the desired health outcomes based on the needs and priorities of the community and your practice. |  | needed
Step 6: Identify Key Drivers of Impact and Secondary Drivers
Goal: To develop a high-level summary of the desired results, key areas the practice intends to focus on to contribute to the desired results, and specific actions the practice needs to take. Key or primary drivers or actions of impact will be identified first and then identify secondary drivers or actions that will lead to key drivers. *Please note: as you complete this section of the gap analysis, the Key Drivers of Impact Tab will be automatically updated with what is entered in the light-blue boxes.
| Recommendations |  | Status | Add Strategies and Key Drivers Below | Person Responsible | Due Date
| Identify potential evidence based strategies that will address the overall practice level impact (AIM) contributing to the community level result (AIM) identified in Step 5. - Use Implementation Resources to help identify these key drivers. |  | needed
| From your list of potential evidence based strategies, identify which of these your practice will adopt. Enter these in the light blue cells. - Use implementation resources to help identify which to adopt. - Once identified, enter the strategies you will adopt in the light blue cells. - These will become your key drivers. |  | needed
needed
needed
needed
needed
needed
| Using the key drivers identified above, describe what changes or actions are needed at the practice level to implement these (e.g., new or revised workflows, scheduling, huddles, referral workflows, EHR documentation, etc.) - Enter the changes or actions needed in the light blue cells. - These will help guide your workplan. |  | needed
needed
needed
needed
needed
needed
needed
needed
needed
needed
needed
needed
Integrating CHWs into Your Practice: Team Preparation and Training
Step 7: Identify Measures of Success and Prepare for Ongoing Evaluation
Goal: To prepare the practice to have the data and quality improvement tools needed to evaluate the effectiveness of implementation; beginning with pilot testing through optimization, spread, and ongoing maintenance of the CHW program. Evaluation plans should answer 4 key questions: (1) What did we do? (2) How much did we do? (3) How well did we do it? (4) Is anyone better off? Completing this section will update the Evaluation and Sustainability tab. *Please note: as you enter information into the light-blue sections below, your Evaluation and Sustainability plan, on tab 6, will be automatically updated with the information you've entered.
| Recommendations |  | Status | Actions Needed | Person Responsible | Due Date
| Begin by reviewing the Key Driver of Impact Tab to focus on the overall practice level aim, key drivers, and secondary drivers. |  | needed
| Work with key stakeholders (including CHWs) to ensure the evaluation reflects community-based principles (e.g. examining how CHWs and community members are meaningfully engaged) and match community priorities. |  | needed
| Identify the added unique value of including CHWs services into your practice. |  | needed
| Using the Key Driver of Impact diagram on Tab 4, identify and define measures of success for the CHW program (e.g. % change, increased patient encounters, patient/staff satisfaction). |  | needed
| Identify sources to collect the data within your evaluation and measurements, including both internal (EHR) and external resources (NCCare360; NC Tracks; CDC tracking data). Collect and record baseline measurement data. |  | needed
| Create a plan based on the indicators of success identified and include a schedule (timeline) of the frequency to collect the data (before, during, and after CHW implementation). |  | needed
| 1. What did we do? The goal of this question is to ensure you understand how the program is being implemented so the team knows what they are evaluating. Refer to "Secondary Drivers" in the Key Driver of Impact diagram on Tab 4. |  | needed
| 2. How much did we do? The goal of this question is to quantify how much of each specific activity/component of the CHW program is being done. This could include Key Drivers or Secondary Drivers. Focus on the activities/components that are the most important. Examples: # of home visits, patient case load, length of visits. |  | needed
| 3. How well did we do it? The goal of this question is to understand how well each specific activity/component (identified in #2 above) of the CHW program is enacted. (Examples: patient satisfaction, % eligible patients referred into the program) |  | needed
| 4. Is anyone better off? The goal of this question is to understand how the program impacts patients, participants, and/or the community. This should include the outcome identified in the Overall Practice-Level Aim and could include additional patient-level outcome measures as secondary aims. Examples: # patients with controlled HgA1C, minutes of physical activity/week, receiving mental health care, etc. |  | needed
| Enactment of this plan is included in Step 10, but will include cycles of program changes for improvement and evaluation of these changes. |  | needed
| After cycles of program improvement, long-term evaluation will include conducting a social return on investment (SROI) and a financial return on investment (ROI). Details are available in Implementation Resources. |  | needed
Step 8: Begin Site Preparation
Goal: To prepare the practice in addressing key administrative and operational needs for an effective and successful CHW program implementation.
| Recommendations |  | Status | Actions Needed | Person Responsible | Due Date
| Review the information in CHW 101 regarding CHW scope of practice and relevant Federal and North Carolina laws. |  | needed
| Define the CHW(s) scope of practice within your care team, based on your established community-level and program/practice-level desired result and impact. |  | needed
| Establish an organizational structure demonstrating how the CHW fits into your care team. |  | needed
| Create job descriptions for CHW Supervisor and CHW. |  | needed
| Develop a budget to estimate the resources and costs associated with the CHW program implementation, include: training, salary, clinical equipment, IT equipment, etc... |  | needed
| Confirm approval for hiring or sub-contracting with a community partner. |  | needed
| If sub-contracting, draft an agreement that includes scope of work, specific deliverables and expectations, and payment. |  | needed
| Recruit, interview and hire CHW Supervisor committed to being an advocate and champion for the CHW role. Recruit, interview, and hire CHW(s), once CHW Supervisor is on board. |  | needed
| Develop CHWs new employee orientation based on ensuring the CHW Supervisor and/or CHW(s) have a good understanding of the organization, the clinical team members, basic EHR knowledge and skills, relevant policies and procedures, relevant clinical workflows, their specific job description and performance expectations, and other items fundamental to becoming a member of the team. |  | needed
| Identify additional training needs for CHW Supervisor and CHW(s) that are specific to their scope of practice and the desired focus of their role based on their job description and the practice level desired impact. |  | needed
| Establish a schedule for reoccurring standing meetings between CHWs and their supervisor and clinical team. |  | needed
| Create written policies and procedures for the CHW(s) role in your practice and within your care team. |  | needed
| Engage the team to map out clinical workflows that include: |  | needed
| 1) the criteria for identifying appropriate patients for CHW services |  | needed
| 2) the referral process |  | needed
| 3) the specific CHW interventions (e.g., initial visit assessments, care plan/health goals, follow up visit frequency and parameters, health education materials, etc.) |  | needed
| 4) the EHR documentation flow |  | needed
| 5) the appropriate and effective type of communication with providers and care team |  | needed
| 6) the frequency to assess clients' health status and determine the continued need for CHW services and when and how to determine when a client has graduated out of the CHW program and removed from the CHW caseload |  | needed
| Identify payer specific potential opportunities for CHWs to contribute to billing for services, e.g., Chronic Care Management (CCM), Transitions of Care Management (TOC), etc. Adapt your workflow accordingly. NOTE: This may not be applicable to all practices. It may also be better to address in the future, once the CHW 's role and workflows are well established. |  | needed
Sustaining CHWs in Your Practice: Assessing CHW Impact and Sustainability in Your Practice
Step 9: Build Awareness and Momentum for the CHW Program
Goal: To create a team and culture that demonstrates the value of the CHW program as it pertains to the improvement of community health and practice population level health outcomes.
| Recommendations |  | Status | Actions Needed | Person Responsible | Due Date
| Develop and implement a structured plan to educate existing and new patients on the role that the CHW will play in their healthcare; include tools or resources that will support a "warm hand-off" from providers." |  | needed
| Develop and implement a plan for educating and building buy-in among providers and care team members (e.g. frontline staff, administrators, payers, supervisors, chief officers, non-management employees, social workers, nurses) for the CHW program. Include CHW roles, anticipated impact, and relevant workflow items. |  | needed
| Develop and implement a plan for conducting regular assessments of the adoption of new workflows. Identify and plan follow up education and trainings to reinforce awareness and expand the knowledge of your providers and care team members. |  | needed
| Establish a regular schedule for CHW(s) to report to practice leadership, providers, and care team members on the CHW program performance, to include individual client stories, common barriers, and resource needs for the practice's patient population. This will reinforce and raise awareness of the current community landscape. |  | needed
Step 10: Plan for Sustainability and Growth of Your CHW Program
Goal: To assess impact of the CHW program, analyze the outcomes, and make necessary program adjustments to optimize success, sustainability, and growth.
| Recommendations |  | Status | Actions Needed | Person Responsible | Due Date
| Assess the impact of your CHW Program. Use the Evaluation & Sustainability Plan in Tab 6 to identify the program impact. |  | needed
| Share evaluation findings with the implementation team, stakeholders, and patients to identify areas for program improvement. |  | needed
| Identify and implement workflow changes to address areas for program improvement identified above. |  | needed
| Repeat these cycles of program evaluation throughout the life of the program to continue this process of quality improvement and optimization. |  | needed
| To ensure sustainability of the program, establish these new and successful workflows in policies and procedures. This will also support onboarding of new CHWs and/or other practice staff. |  | needed
| Support growth of CHW programs by investing in training and professional development of CHWs, CHW Supervisors, and other practice staff. |  | needed
| Analyze key CHW program measures (key drivers) that will help describe the return on investment (ROI), such as impact on access to care, patient experience, health outcomes, utilization, cost, etc. |  | needed
| Ensure your practice budget is updated to incorporates on-going CHW-program costs (e.g., continuous training, salary, properly equipping CHWs, etc.). |  | needed
| Consider areas for program growth such as: expanding the program goals based on patient and community needs, hiring additional CHWs and support staff, investing in new and/or additional equipment, etc. |  | needed

## 4. Key Drivers of Impact
Key Drivers of Impact
Purpose | The purpose of the key drivers of impact is to provide you an overview of the program, showing the relationship between the AIMS, Key Drivers, and Secondary Drivers of the program. This will serve as a quick reference and will be useful in later steps of the Gap Analysis. The practice will build measures of success around this plan and should refer to it regularly as a reminder of the overall goals you are trying to achieve. Make updates to the plan as necessary to reflect ongoing learnings accomplished by your team.
Instructions | After completing sections 5 and 6 in the Gap Analysis tab, this table will be automatically updated with your program plan. This plan will be referred to when developing and enacting your evaluation and sustainability plan and should be kept up to date with the actual changes/actions/activities enacted as part of this plan.
AIMS |  | Key Drivers What Evidence Based Strategies will the practice adopt and implement to help achieve AIM? | Secondary Drivers What changes or actions are needed at the practice level to implement Key Drivers?
0 |  | 0 | 0
0
|  | 0 | 0
0 |  |  | 0
|  | 0 | 0
0
|  | 0 | 0
0
|  | 0 | 0
0
|  | 0 | 0
0

## 5. Project Management Plan
Project Management Plan
Purpose | The purpose of the project management plan is to provide a running list of tasks, derived from the Gap Analysis, to be completed by the practice.
Instructions | Currently, all tasks in the Gap Analysis appear here. As tasks are marked "Completed" they will be removed. Tasks can be sorted by person responsible, due date, or topic to help with project management.
Planning Group Leader |  | Community Partners |  | Practice Departments & Members | Meeting Time
TBD |  | TBD |  | TBD | TBD
Planning Group Members
TBD
Recommendations | 0 | Status | Actions Needed | Person Responsible | Due Date
Identify a planning group leader. | 0 | needed | 0 | 0 | 0
Begin by reviewing the Key Driver of Impact Tab to focus on the overall practice level aim, key drivers, and secondary drivers. | 0 | needed | 0 | 0 | 0
Identify community partners and community members, including patients, to be part of your program planning. If you do not have existing relationships - focus on Step 3 below. | 0 | needed | 0 | 0 | 0
Identify members of the practice across all departments and/or areas impacted by this change. | 0 | needed | 0 | 0 | 0
Identify a regularly scheduled meeting at a time that allows all team members to attend. | 0 | needed | 0 | 0 | 0
Identify time for team members, outside of the meeting times, to work on action items. | 0 | needed | 0 | 0 | 0
Create written team charter outlining team member roles, meeting times, and the purpose of the team. | 0 | needed | 0 | 0 | 0
Understand CHWs’ potential roles and contributions to patient outcomes, as well as their core competencies (knowledge, skills and abilities). | 0 | needed | 0 | 0 | 0
Identify Federal and North Carolina laws and policies influencing CHW integration in health care settings (e.g. CHW core competencies, scope of practice, certification, financing, HIPAA). | 0 | needed | 0 | 0 | 0
Identify internal and external stakeholders who will be essential in your CHW program (e.g. CHWs, community partners, program participants, health care managers). | 0 | needed | 0 | 0 | 0
Identify the roles each stakeholder will have within your CHW program. Consider sub-contracting directly with a CBO CHW service provider as a strategy. | 0 | needed | 0 | 0 | 0
Identify ways in which you will engage key stakeholders initially and on a continuous basis (e.g. CHW advisory groups, town hall meetings, in-person briefings, newsletter). | 0 | needed | 0 | 0 | 0
Identify and use approaches to gain input from all community partners when developing program goals and objectives. | 0 | needed | 0 | 0 | 0
Understand who is in your community, by identifying the following: population demographics, social landscape (income/poverty, education, health insurance), languages spoken, culture, life experiences, economics and technology differences across your community. | 0 | needed | 0 | 0 | 0
Understand the population served by your practice by identifying the following: population demographics, social landscape (income/poverty, education, health insurance), languages spoken, culture, life experiences, economics and technology differences across your community. | 0 | needed | 0 | 0 | 0
Work with your expanded team, including patients and/or community partners, to identify several community-level and related practice-level improvement opportunities for CHW services to address. | 0 | needed | 0 | 0 | 0
Identify which of the community and practice opportunities are priorities and can be effectively addressed by CHWs. | 0 | needed | 0 | 0 | 0
Identify the overall community health improvement result (AIM) that your practice will contribute to as one of the many partners in your community working together collectively. Include community partners, stakeholders, and/or patients as part of this work. | 0 | needed | 0 | 0 | 0
Identify the overall practice level impact (AIM) to focus on, using evidence-based CHW strategies and interventions. Identify the specific population(s), as well as the desired health outcomes based on the needs and priorities of the community and your practice. | 0 | needed | 0 | 0 | 0
Identify potential evidence based strategies that will address the overall practice level impact (AIM) contributing to the community level result (AIM) identified in Step 5. - Use Implementation Resources to help identify these key drivers. | 0 | needed | 0 | 0 | 0
From your list of potential evidence based strategies, identify which of these your practice will adopt. Enter these in the light blue cells. - Use implementation resources to help identify which to adopt. - Once identified, enter the strategies you will adopt in the light blue cells. - These will become your key drivers. | 0 | needed | 0 | 0 | 0
0 | 0 | needed | 0 | 0 | 0
0 | 0 | needed | 0 | 0 | 0
0 | 0 | needed | 0 | 0 | 0
0 | 0 | needed | 0 | 0 | 0
0 | 0 | needed | 0 | 0 | 0
Using the key drivers identified above, describe what changes or actions are needed at the practice level to implement these (e.g., new or revised workflows, scheduling, huddles, referral workflows, EHR documentation, etc.) - Enter the changes or actions needed in the light blue cells. - These will help guide your workplan. | 0 | needed | 0 | 0 | 0
0 | 0 | needed | 0 | 0 | 0
|  | needed | 0 | 0 | 0
|  | needed | 0 | 0 | 0
|  | needed | 0 | 0 | 0
|  | needed | 0 | 0 | 0
|  | needed | 0 | 0 | 0
|  | needed | 0 | 0 | 0
0 | 0 | needed | 0 | 0 | 0
#REF! | #REF! | needed | 0 | 0 | 0
#REF! | #REF! | needed | 0 | 0 | 0
#REF! | #REF! | needed | 0 | 0 | 0
Begin by reviewing the Key Driver of Impact Tab to focus on the overall practice level aim, key drivers, and secondary drivers. | 0 | needed | 0 | 0 | 0
Work with key stakeholders (including CHWs) to ensure the evaluation reflects community-based principles (e.g. examining how CHWs and community members are meaningfully engaged) and match community priorities. | 0 | needed | 0 | 0 | 0
Identify the added unique value of including CHWs services into your practice. | 0 | needed | 0 | 0 | 0
Using the Key Driver of Impact diagram on Tab 4, identify and define measures of success for the CHW program (e.g. % change, increased patient encounters, patient/staff satisfaction). | 0 | needed | 0 | 0 | 0
Identify sources to collect the data within your evaluation and measurements, including both internal (EHR) and external resources (NCCare360; NC Tracks; CDC tracking data). Collect and record baseline measurement data. | 0 | needed | 0 | 0 | 0
Create a plan based on the indicators of success identified and include a schedule (timeline) of the frequency to collect the data (before, during, and after CHW implementation). | 0 | needed | 0 | 0 | 0
1. What did we do? The goal of this question is to ensure you understand how the program is being implemented so the team knows what they are evaluating. Refer to "Secondary Drivers" in the Key Driver of Impact diagram on Tab 4. | 0 | needed | 0 | 0 | 0
2. How much did we do? The goal of this question is to quantify how much of each specific activity/component of the CHW program is being done. This could include Key Drivers or Secondary Drivers. Focus on the activities/components that are the most important. Examples: # of home visits, patient case load, length of visits. | 0 | needed |  | 0 | 0
3. How well did we do it? The goal of this question is to understand how well each specific activity/component (identified in #2 above) of the CHW program is enacted. (Examples: patient satisfaction, % eligible patients referred into the program) | 0 | needed | 0 | 0 | 0
4. Is anyone better off? The goal of this question is to understand how the program impacts patients, participants, and/or the community. This should include the outcome identified in the Overall Practice-Level Aim and could include additional patient-level outcome measures as secondary aims. Examples: # patients with controlled HgA1C, minutes of physical activity/week, receiving mental health care, etc. | 0 | needed | 0 | 0 | 0
Enactment of this plan is included in Step 10, but will include cycles of program changes for improvement and evaluation of these changes. | 0 | needed | 0 | 0 | 0
After cycles of program improvement, long-term evaluation will include conducting a social return on investment (SROI) and a financial return on investment (ROI). Details are available in Implementation Resources. | 0 | needed | 0 | 0 | 0
Review the information in CHW 101 regarding CHW scope of practice and relevant Federal and North Carolina laws. | 0 | needed | 0 | 0 | 0
Define the CHW(s) scope of practice within your care team, based on your established community-level and program/practice-level desired result and impact. | 0 | needed | 0 | 0 | 0
Establish an organizational structure demonstrating how the CHW fits into your care team. | 0 | needed | 0 | 0 | 0
Create job descriptions for CHW Supervisor and CHW. | 0 | needed | 0 | 0 | 0
Develop a budget to estimate the resources and costs associated with the CHW program implementation, include: training, salary, clinical equipment, IT equipment, etc... | 0 | needed | 0 | 0 | 0
Confirm approval for hiring or sub-contracting with a community partner. | 0 | needed | 0 | 0 | 0
If sub-contracting, draft an agreement that includes scope of work, specific deliverables and expectations, and payment. | 0 | needed | 0 | 0 | 0
Recruit, interview and hire CHW Supervisor committed to being an advocate and champion for the CHW role. Recruit, interview, and hire CHW(s), once CHW Supervisor is on board. | 0 | needed | 0 | 0 | 0
Develop CHWs new employee orientation based on ensuring the CHW Supervisor and/or CHW(s) have a good understanding of the organization, the clinical team members, basic EHR knowledge and skills, relevant policies and procedures, relevant clinical workflows, their specific job description and performance expectations, and other items fundamental to becoming a member of the team. | 0 | needed | 0 | 0 | 0
Identify additional training needs for CHW Supervisor and CHW(s) that are specific to their scope of practice and the desired focus of their role based on their job description and the practice level desired impact. | 0 | needed | 0 | 0 | 0
Establish a schedule for reoccurring standing meetings between CHWs and their supervisor and clinical team. | 0 | needed | 0 | 0 | 0
Create written policies and procedures for the CHW(s) role in your practice and within your care team. | 0 | needed | 0 | 0 | 0
Engage the team to map out clinical workflows that include: | 0 | needed | 0 | 0 | 0
1) the criteria for identifying appropriate patients for CHW services | 0 | needed | 0 | 0 | 0
2) the referral process | 0 | needed | 0 | 0 | 0
3) the specific CHW interventions (e.g., initial visit assessments, care plan/health goals, follow up visit frequency and parameters, health education materials, etc.) | 0 | needed | 0 | 0 | 0
4) the EHR documentation flow | 0 | needed | 0 | 0 | 0
5) the appropriate and effective type of communication with providers and care team | 0 | needed | 0 | 0 | 0
6) the frequency to assess clients' health status and determine the continued need for CHW services and when and how to determine when a client has graduated out of the CHW program and removed from the CHW caseload | 0 | needed | 0 | 0 | 0
Identify payer specific potential opportunities for CHWs to contribute to billing for services, e.g., Chronic Care Management (CCM), Transitions of Care Management (TOC), etc. Adapt your workflow accordingly. NOTE: This may not be applicable to all practices. It may also be better to address in the future, once the CHW 's role and workflows are well established. | 0 | needed | 0 | 0 | 0
Develop and implement a structured plan to educate existing and new patients on the role that the CHW will play in their healthcare; include tools or resources that will support a "warm hand-off" from providers." | 0 | needed | 0 | 0 | 0
Develop and implement a plan for educating and building buy-in among providers and care team members (e.g. frontline staff, administrators, payers, supervisors, chief officers, non-management employees, social workers, nurses) for the CHW program. Include CHW roles, anticipated impact, and relevant workflow items. | 0 | needed | 0 | 0 | 0
Develop and implement a plan for conducting regular assessments of the adoption of new workflows. Identify and plan follow up education and trainings to reinforce awareness and expand the knowledge of your providers and care team members. | 0 | needed | 0 | 0 | 0
Establish a regular schedule for CHW(s) to report to practice leadership, providers, and care team members on the CHW program performance, to include individual client stories, common barriers, and resource needs for the practice's patient population. This will reinforce and raise awareness of the current community landscape. | 0 | needed | 0 | 0 | 0
Assess the impact of your CHW Program. Use the Evaluation & Sustainability Plan in Tab 6 to identify the program impact. | 0 | needed | 0 | 0 | 0
Share evaluation findings with the implementation team, stakeholders, and patients to identify areas for program improvement. | 0 | needed | 0 | 0 | 0
Identify and implement workflow changes to address areas for program improvement identified above. | 0 | needed | 0 | 0 | 0
Repeat these cycles of program evaluation throughout the life of the program to continue this process of quality improvement and optimization. | 0 | needed | 0 | 0 | 0
To ensure sustainability of the program, establish these new and successful workflows in policies and procedures. This will also support onboarding of new CHWs and/or other practice staff. | 0 | needed | 0 | 0 | 0
Support growth of CHW programs by investing in training and professional development of CHWs, CHW Supervisors, and other practice staff. | 0 | needed | 0 | 0 | 0
Analyze key CHW program measures (key drivers) that will help describe the return on investment (ROI), such as impact on access to care, patient experience, health outcomes, utilization, cost, etc. | 0 | needed | 0 | 0 | 0
Ensure your practice budget is updated to incorporates on-going CHW-program costs (e.g., continuous training, salary, properly equipping CHWs, etc.). | 0 | needed | 0 | 0 | 0
Consider areas for program growth such as: expanding the program goals based on patient and community needs, hiring additional CHWs and support staff, investing in new and/or additional equipment, etc. | 0 | needed | 0 | 0 | 0

## 6. Evaluation & Sustainability
Evaluation & Sustainability Plan
Purpose | The purpose of the evaluation and sustainability plan is to provide an overview of the program evaluation and sustainability plan by providing a flow chart demonstrating the steps needed for evaluation. This will serve as a quick reference and will be useful for conducting the Evaluation.
Instructions | After completing step 7 in the Gap Analysis tab, this flow chart will be automatically updated with your Evaluation plan. This plan will be referred to when conducting evaluation and developing a sustainability plan and should be kept up to date with the actual measures of success identified as part of the evaluation plan.
What did we do? Is the CHW program being enacted as intended?
0
| Yes | No
How much did we do? (enough, too much, not enough)
0
How well did we do it? (good, needs improvement)
0
Is anyone better off? (yes, no, maybe)
0
| enough, good, yes | too much/not enough, needs improvement, no/maybe
| Use feedback from CHWs and patients to decide what improvements, if any, are needed | Identify areas for improvement to improve the answers to the questions: how much, how well, is anyone better off?
Using the improvements and/or changes identified in the step above, update the Key Driver of impact plan using Step 7 of the Gap analysis, and complete another cycle of implementation and evaluation to test the impact of these changes.
Once the program has been optimized, develop a long term sustainability and evaluation plan.
Sustainability, and Growth
Social ROI
Financial ROI
Update Secondary Drivers with what was actually done.
cycles of program improvement

## 7. Implementation Resources
Implementation Resources
Purpose | The purpose of the implementation resources is to provide resources to address any gaps identified on the gap analysis and support overall implementation of CHW services.
Instructions | The resources below are organized according to the sections outlined in the Overview and Gap Analysis tabs. Below are links to websites, additional documents, and written content. We anticipate additional resources will be added as new information becomes available. Please use them to increase your knowledge and help you develop your program.
This is a living document. Resources will be added and revised on a periodic basis. If you have suggestions for additional resources please contact Katherine.Andersen@seahec.net.
Step 1: Form A Team
Key Topics |  | Resources
Use the team checklist developed by MIT to draft a team charter - purpose, time commitment, scope of work, team members, reporting schedule, desired results, measurement of success |  | MIT Human Resources. Important Steps when Building a New Team. Accessed October 29, 2021. https://hr.mit.edu/learning-topics/teams/articles/new-team
Step 2: Learn about CHWs
Key Topics |  | Resources
American Public Health Association CHW Section Page - Definition and Resources |  | American Public Health Association. Community Health Workers. Accessed October 29, 2021. https://www.apha.org/apha-communities/member-sections/community-health-workers
NC DHHS Final Report on Stakeholder Recommendations of the NC CHW Initiative - CHW titles, roles and core competencies |  | North Carolina Department of Health and Human Services. Community Health Workers in North Carolina: Creating an Infrastructure for Sustainability. NC Department of Health and Human Services; 2018:40. Accessed October 29, 2021. https://www.ncdhhs.gov/media/6628/download
C3 Project - CHW Roles, Core Competencies, and Qualities |  | Community Health Worker Core Consensus (C3) Project. C3 Project Findings: Roles & Competencies. Accessed October 29, 2021. https://www.c3project.org/roles-competencies
C3 Project Website - CHW Roles and Competencies Review Checklist |  | Community Health Worker Core Consensus (C3) Project. C3 Project CHW Roles and Competencies Review Checklist. Accessed October 29, 2021. https://0d6c00fe-eae1-492b-8e7d-80acecb5a3c8.filesusr.com/ugd/7ec423_cb744c7b87284c75af7318614061c8ec.pdf
Roles and Functions of CHWs in Primary Care |  | Hartzler AL, Tuzzio L, Hsu C, Wagner EH. Roles and Functions of Community Health Workers in Primary Care. The Annals of Family Medicine. 2018;16(3):240-245. doi:10.1370/afm.2208
NC CHW Initiative |  | North Carolina Department of Health and Human Services (NC DHHS). Community Health Worker Initiative. Accessed October 29, 2021. https://www.ncdhhs.gov/about/department-initiatives/healthy-opportunities/community-health-worker-initiative
Step 3: Build Authentic Community Relationships
Key Topics |  | Resources
Identify key stakeholders in the community with the goal of building relationships for bi-directional communication. This will include both health and social partnerships. | Health- Local Health Department, Regional Hospital, Dental Providers, Counseling Services, Rehabilitation Services/Facilities. | Community Health Resources
| Social- Local Churches/Religious Organizations, Activity Centers, Schools, Department of Social Services, Law Enforcement | Community Social Resources
Authentic Community Engagement
Primary Health Care Performance Initiative (PHCPI) |  | Primary Health Care Performance Initiative (PHCPI). Community Engagement. Published September 28, 2018. Accessed October 29, 2021. https://improvingphc.org/improvement-strategies/population-health-management/community-engagement
JAMA: Trust Between Health Care and Community Organizations |  | Stout SS, Simpson LA, Singh P. Trust Between Health Care and Community Organizations. JAMA. 2019;322(2):109. doi:10.1001/jama.2019.1211
IHI: It's Not You. It's Us: Earning Trust to Build Community Connections |  | Institute for Healthcare Improvement (IHI). It’s Not You, It’s Us: Earning Trust to Build Community Connections. Published June 17, 2021. Accessed October 29, 2021. http://www.ihi.org/communities/blogs/its-not-you-its-us-earning-trust-to-build-community-connections
Step 4: Identify Community and Practice Level Opportunities to Advance Health for All
Key Topics |  | Resources
Know your community's basic characteristics including demographics (age, race, ethnicity) as well as broader perspectives and community norms and culture. This will also include an overview of Population Health. | Community Assessment Considerations: age, race, ethnicity, socio-economic landscape, religious representation, language spoken, safe schools/neighborhoods. | Community Health Assessment
Population Health Considerations: Obesity rates, infant mortality rates, Insurance/payor breakdown, food security, Drug/overdose rates.
Step 5: Establish Overall Desired Result/Impact
Key Topics |  | Resources
Identify population-level health improvement desired result for your practice to contribute to. |  | Establish Overall Desired Results
Identify practice-level impact that can contribute to overall desired result. Numerous EHR’s exist for practices, and the workflows and capabilities vary. It is important for the CHW to have adequate log in credentials to the EHR and their patient’s records with the access level determined by the practice. For specific questions and specifications, contact your EHR vendor.
Smart Goals Sheet
EHR Considerations
Step 6: Identify Key Drivers of Impact
Key Topics |  | Resources
Establishing Key Drivers of Impact |  | Mapping Out Key Driver Diagram
Evidence-Based Practices and Interventions |  | EBP CHW Program Planning
Step 7: Identify Measures of Success and Prepare for Ongoing Evaluation
Key Topic |  | Resource
Nationally Endorsed CHW Program Evaluation Measures |  | CHW Center for Research and Evaluation Common Indicators
NC Medicaid Quality Performance Measures |  | NC Medicaid Quality Measure Performance and Targets for the AMH Measure Set
Step 8: Begin Site Preparation
Hiring
Key Topics |  | Resources
Hiring Justification |  | Lehmann U, Sanders D. Community Health Workers: What Do We Know about Them? The State of the Evidence on Programmes, Activities, Costs and Impact on Health Outcomes of Using Community Health Workers. World Health Organization; 2007. Accessed October 29, 2021. https://www.who.int/hrh/documents/community_health_workers.pdf
Community Health Worker Scope of Work/HR Considerations Overview |  | Overview Document
Role and Job Descriptions: CHW and CHW Supervisor |  | Community Health Worker Core Competency (C3) Project. C3 Project CHW Roles and Competencies Review Checklist. Accessed October 29, 2021. https://0d6c00fe-eae1-492b-8e7d-80acecb5a3c8.filesusr.com/ugd/7ec423_cb744c7b87284c75af7318614061c8ec.pdf
Cost Analysis |  | Mirambeau AM, Wang G, Ruggles L, Dunet DO. A Cost Analysis of a Community Health Worker Program in Rural Vermont. J Community Health. 2013;38(6):1050-1057. doi:10.1007/s10900-013-9713-x
Reporting Structure |  | Example: MAHEC Community and Home Visits
Example: CHW Program Operations Guide
Facilities & IT Needs |  | Workforce Options
Onboarding and Training
Key Topics |  | Resources
NC CHW Core Curriculum |  | North Carolina Department of Health and Human Services. Community Health Worker Training. Accessed October 29, 2021. https://www.ncdhhs.gov/divisions/office-rural-health/community-health-workers/community-health-worker-training
CHW Specialty Training to Prepare for Partnership and Integration into AMHs |  | NC AHEC CHW Website
C3 Project Framework for Assessing CHW Skills Proficiency and Fostering Professional Development |  | Allen CG, Brownstein JN, Cole M, Hirsch G. Community Health Worker Assessment Toolkit: A Framework for Assessing Skills Proficiency and Fostering Professional Development. Community Health Worker Core Consensus (C3) Project; 2018. Accessed October 29, 2021. https://0d6c00fe-eae1-492b-8e7d-80acecb5a3c8.filesusr.com/ugd/7ec423_c3c4b559904d417e851c5dfb5ab25bc8.pdf
C3 Project Guidelines for CHW Skills Assessment
Additional CHW Training |  | CHW and Supervisor Professional Development Resources
Sub-Contracting with Community Based CHW Service Provider
Key Topics |  | Resources
Contracting an external CHW |  | Example: CHW Services MOU
ABIPA-MAHEC CHW Partnership Program Design
Contracting with Community-Based CHW Service Provider
Additional resources that outline the benefits of and how to of collaborations between healthcare and community-based organizations |  | Meals on Wheels, Quantified Ventures. Effective Partnerships Between Community-Based Organizations and Healthcare: A Possible Path to Sustainability. Meals on Wheels; 2018. Accessed October 29, 2021. https://www.mealsonwheelsamerica.org/docs/default-source/research/effective-partnerships-between-cbos-and-healthcare_full-report_final.pdf?sfvrsn=8e5fbf3b_2
Association of State and Territorial Health Officials. Collaborations Between Health Systems and Community-Based Organizations: Executive Summary. Association of State and Territorial Health Officials; 2020:10. Accessed October 29, 2021. https://astho.org/ASTHOReports/Collaborations-Between-Health-Systems-Community-Based-Organizations/01-31-20/
Clinical Workflows and EHR Documentation
Key Topics |  | Resources
Establishing Clinical Workflows |  | Example: CHW Service Work Flows
CHW Billing Resource |  | Community Health Worker Billing Resource
Step 9: Build Awareness and Momentum for the CHW Program
Key Topic |  | Resource
The Prosci ADKAR® Model - simple 5 steps in successful and sustainable organizational change. It begins with helping people to understand the why or awareness of the need for change and engaging them in the desire to support and participate in the change. |  | The Prosci ADKAR Model ¦ Prosci Tim Talks. Prosci; 2019. Accessed October 29, 2021. https://www.youtube.com/watch?v=L_7I03LOyyk
NC AHEC CHW Video Library |  | What is a CHW?
Regular presentations about the services and impact as well as what CHWs are learning and hearing from clients will support continued momentum and support for the program. |  | CHW Quarterly Reports Tip Sheet
Step 10: Prepare for Spread and Optimization of the Program
Key Topic |  | Resource
Practices that have access to payer cost information can calculate an ROI forecast that could be used to seek additional funding for CHW programs. |  | Center for Healthcare Strategies, Inc. ROI Forecasting Calculator. Published 2011. Accessed October 29, 2021. https://chcsroihealthhomes.org/Welcome.aspx
Additional Resources
Key Topic |  | Resource
Supplemental resources developed to support CHW integration into practice settings.

## Sheet2 (hidden)
| Practice | Ready | YES
| CIN | In Progress | NO
| Unsure | Needed
E3 Lookup
#REF! | #REF!
Ready

## 8. CHW FAQs
CHW FAQs
Purpose | The purpose of the CW FAQs is to provide additional information about CHWs based on practical questions that are common to practices exploring or actively implementing CHW services and programs.
Instructions | Review responses listed below.
CHW Frequently Asked Questions (FAQs)
What is the difference between CHWs and Peer Support Specialists (PSSs)? |  | Peer Support Specialists are a sub-set of CHWs who have lived-experience with illness and/or health and/or substance use disorder. There is a separate training and certification process for becoming a Certified Peer Support Specialist in NC. While all PSS are CHWs, not all CHWs are qualified to become PSSs. For more information visit the NC Certified Peer Support Specialist Program website (link below).
University of North Carolina Chapel Hill, School of Social Work. Welcome to the NC Certified Peer Support Specialist Program. NC Peer Support Specialist Certification Program. Accessed November 9, 2021. https://pss.unc.edu/
What is lived experience? |  | The Oxford Dictionary defines "lived experience" as "[p]personal knowledge about the world gained through direct, first-hand involvement in everyday events rather than through representations constructed by other people. It may also refer to knowledge of people gained from direct face-to-face interaction rather than through a technological medium."1 The Lived Experience project defines it as "[t]he experience(s) of people on whom a social issue, or combination of issues, has had a direct impact."2
References: 1. Sandhu B. The Value of Lived Experience in Social Change: The Need for Leadership and Organisational Development in the Social Sector. The Lived Experience; 2017. Accessed November 9, 2021. http://thelivedexperience.org/report/ 2. Oxford Reference. lived experience. doi:10.1093/oi/authority.20110803100109997
Can CHWs provide clinical services? |  | CHWs function independently as frontline public health workers and do not provide clinical services. However, falling under the role of health promotion and education, CHWs can perform assessments and connect community members to resources, including health services. When working in partnership with healthcare providers, CHWs can play a role in assessing vital signs and other psychosocial factors and connecting patients to provider services through remote communication (e.g., telehealth, telephone). They can also provide basic clinical services, such as first aid (e.g., dressing changes) and directed exams for common problems (e.g., diabetic foot exams). In all of these cases, it is important for the employers and supervisors to set up a process for training, competency assessment, and supervision. Employers will also want to be aware of the scope of practice and regulations that guide individual staff involved in supervising CHWs, (e.g., NC Board of Nursing if an RN is supervising CHWs). Lastly, oftentimes CHWs may have other certifications and licenses, such as CNA, CPSS, etc. It is important for employers and supervisors to be aware of the requirements of these certifications and licenses when planning roles, responsibilities and workflows for CHWs.
Is there CHW Certification in NC? |  | The NC CHW Association is responsible for the CHW certification program. Foundational certification is currently being built around completion of a CHW Core Curriculum offered at community colleges across the state. There will also be a legacy path to certification for CHWs currently working in NC. Maintenance of Certification will include completion of a required # of CEUs over a specific period of time. As of 10/1/2021, a date for launching a formal certification program has not yet been established. For more information about community colleges offering CHW Core Curriculum visit the NC DHHS CHW Initiative CHW Training webpage (link below).
North Carolina Department of Health and Human Services. Community Health Worker Training. Accessed October 29, 2021. https://www.ncdhhs.gov/divisions/office-rural-health/community-health-workers/community-health-worker-training
What is the NC CHW Initiative? |  | NC Department of Health and Human Services established the NC CHW Initiative in 2015 to promote the development and spread of sustainable infrastructure for CHWs and CHW programs across the state. This work is led by the Office of Rural Health and includes a number of key anchor partners. Core to the Initiative is the NC CHW Association, the professional organization for CHWs across the state. For more information visit the NC DHHS CHW Initiative webpage (link below).
North Carolina Department of Health and Human Services (NC DHHS). Community Health Worker Initiative. Accessed October 29, 2021. https://www.ncdhhs.gov/about/department-initiatives/healthy-opportunities/community-health-worker-initiative

## 9. References
References
CHW 101
1. Massachusetts Department of Public Health. Achieving the Triple Aim: Success with Community Health Workers. Massachusetts Department of Public Health; 2015:12. Accessed November 9, 2021. https://www.mass.gov/doc/achieving-the-triple-aim-success-with-community-health-workers-0/download
2. Utah Department of Health, Environment, Policy and Improved Clinical Care (EPICC) Program. Community Health Worker Stories. Accessed October 29, 2021. https://heal.health.utah.gov/wp-content/uploads/2021/11/CHW-stories_2_25_20.pdf
3. Brooks BA, Davis S, Frank-Lightfoot L, Kulbok PA, Poree S, Sgarlata L. Building A Community Health Worker Program: The Key to Better Care, Better Outcomes, & Lower Costs. CommunityHealth Works; 2018:57. Accessed October 29, 2021. https://www.aha.org/system/files/2018-10/2018-chw-program-manual-toolkit.pdf
4. Gutierrez KA, Campbell. Best Practice Guidelines for Implementing and Evaluating Community Health Worker Programs in Health Care Settings. Sinai Urban Health Institute; 2014:151. Accessed October 29, 2021. https://chwcentral.org/wp-content/uploads/2014/01/CHW-BPG-for-CHW-programs-in-health-care-settings.pdf
5. Rural Health Information Hub (RHIhub). Advantages of Community Health Workers in Rural Health Settings. Accessed October 29, 2021. https://www.ruralhealthinfo.org/toolkits/community-health-workers/1/advantages
6. Kangovi S, Nandita M, Grande D, Long J, Asch D. Evidence-Based Community Health Worker Program Addresses Unmet Social Needs And Generates Positive Return On Investment. Health Affairs. 2020;39(2). doi:10.1377/hlthaff.2019.00981
7. Association of State and Territorial Health Officials (ASTHO), National Association of Community Health Workers (NACHW). Community Health Workers: Evidence of Their Effectiveness. ASTHO Accessed October 29, 2021. https://www.astho.org/Programs/Clinical-to-Community-Connections/Documents/CHW-Evidence-of-Effectiveness/
8. Boston University School of Social Work, Center for Innovation in Social Work and Health. Unpacking a Client’s Past to Move Forward: A Community Health Worker Intervention Story. CHW News Articles. Published April 1, 2019. Accessed October 29, 2021. https://ciswh.org/community-health-worker-intervention-story/
9. C3 Project. What Is a CHW? Core Roles and Competencies from the C3 Project.; 2018. Accessed October 29, 2021. https://www.youtube.com/watch?v=hUv5KBXjxKE
10. American Public Health Association. Community Health Workers. Accessed October 29, 2021. https://www.apha.org/apha-communities/member-sections/community-health-workers
11. Community Health Workers ¦ NCDHHS. Accessed September 20, 2021. https://www.ncdhhs.gov/divisions/office-rural-health/community-health-workers
12. Roles & Competencies ¦ CHW Core Consensus Project. CHW Core Consensus P. Accessed September 20, 2021. https://www.c3project.org/roles-competencies
Gap Analysis
1. Centers for Disease Control and Prevention. Including Community Health Workers in Health Care Settings: A Checklist for Public Health Practitioners. Version 1.0. Centers for Disease Control and Prevention; 2019:3. Accessed November 18, 2021. https://www.cdc.gov/dhdsp/pubs/docs/CHW_Integration_Checklist.pdf
Implementation Resources
1. Community Health Worker Core Consensus (C3) Project. C3 Project CHW Roles and Competencies Review Checklist. Accessed October 29, 2021. https://0d6c00fe-eae1-492b-8e7d-80acecb5a3c8.filesusr.com/ugd/7ec423_cb744c7b87284c75af7318614061c8ec.pdf
2. North Carolina Department of Health and Human Services. Community Health Worker Training. Accessed October 29, 2021. https://www.ncdhhs.gov/divisions/office-rural-health/community-health-workers/community-health-worker-training
3. North Carolina Department of Health and Human Services (NC DHHS). Community Health Worker Initiative. Accessed October 29, 2021. https://www.ncdhhs.gov/about/department-initiatives/healthy-opportunities/community-health-worker-initiative
4. Center for Healthcare Strategies, Inc. ROI Forecasting Calculator. Published 2011. Accessed October 29, 2021. https://chcsroihealthhomes.org/Welcome.aspx
5. Institute for Healthcare Improvement. Improving Health Equity: Assessment Tool for Health Care Organizations. Institute for Healthcare Improvement; 2019. Accessed October 29, 2021. https://wispqc.org/wp-content/uploads/2021/05/IHI_ImprovingHealthEquity_AssessmentTool.pdf
6. Institute for Healthcare Improvement. Tool: How to Know Where to Go on Health Equity. Published March 12, 2020. Accessed October 29, 2021. http://www.ihi.org/communities/blogs/how-to-know-where-to-go-on-health-equity
7. The Prosci ADKAR Model ¦ Prosci Tim Talks. Prosci; 2019. Accessed October 29, 2021. https://www.youtube.com/watch?v=L_7I03LOyyk
8. Association of State and Territorial Health Officials. Collaborations Between Health Systems and Community-Based Organizations: Executive Summary. Association of State and Territorial Health Officials; 2020:10. Accessed October 29, 2021. https://astho.org/ASTHOReports/Collaborations-Between-Health-Systems-Community-Based-Organizations/01-31-20/
9. Meals on Wheels, Quantified Ventures. Effective Partnerships Between Community-Based Organizations and Healthcare: A Possible Path to Sustainability. Meals on Wheels; 2018. Accessed October 29, 2021. https://www.mealsonwheelsamerica.org/docs/default-source/research/effective-partnerships-between-cbos-and-healthcare_full-report_final.pdf?sfvrsn=8e5fbf3b_2
10. Allen CG, Brownstein JN, Cole M, Hirsch G. Community Health Worker Assessment Toolkit: A Framework for Assessing Skills Proficiency and Fostering Professional Development. Community Health Worker Core Consensus (C3) Project; 2018. Accessed October 29, 2021. https://0d6c00fe-eae1-492b-8e7d-80acecb5a3c8.filesusr.com/ugd/7ec423_c3c4b559904d417e851c5dfb5ab25bc8.pdf
11. Mirambeau AM, Wang G, Ruggles L, Dunet DO. A Cost Analysis of a Community Health Worker Program in Rural Vermont. J Community Health. 2013;38(6):1050-1057. doi:10.1007/s10900-013-9713-x
12. Lehmann U, Sanders D. Community Health Workers: What Do We Know about Them? The State of the Evidence on Programmes, Activities, Costs and Impact on Health Outcomes of Using Community Health Workers. World Health Organization; 2007. Accessed October 29, 2021. https://www.who.int/hrh/documents/community_health_workers.pdf
13. Institute for Healthcare Improvement (IHI). It’s Not You, It’s Us: Earning Trust to Build Community Connections. Published June 17, 2021. Accessed October 29, 2021. http://www.ihi.org/communities/blogs/its-not-you-its-us-earning-trust-to-build-community-connections
14. Stout SS, Simpson LA, Singh P. Trust Between Health Care and Community Organizations. JAMA. 2019;322(2):109. doi:10.1001/jama.2019.1211
15. American Medical Association. Prioritizing Equity video series: Sharing power through alliances. Published May 3, 2021. Accessed October 29, 2021. https://www.ama-assn.org/delivering-care/health-equity/prioritizing-equity-video-series-sharing-power-through-alliances
16. Primary Health Care Performance Initiative (PHCPI). Community Engagement. Published September 28, 2018. Accessed October 29, 2021. https://improvingphc.org/improvement-strategies/population-health-management/community-engagement
17. Hartzler AL, Tuzzio L, Hsu C, Wagner EH. Roles and Functions of Community Health Workers in Primary Care. The Annals of Family Medicine. 2018;16(3):240-245. doi:10.1370/afm.2208
18. Community Health Worker Core Consensus (C3) Project. C3 Project Findings: Roles & Competencies. Accessed October 29, 2021. https://www.c3project.org/roles-competencies
19. North Carolina Department of Health and Human Services. Community Health Workers in North Carolina: Creating an Infrastructure for Sustainability. NC Department of Health and Human Services; 2018:40. Accessed October 29, 2021. https://www.ncdhhs.gov/media/6628/download
20. MIT Human Resources. Important Steps when Building a New Team. Accessed October 29, 2021. https://hr.mit.edu/learning-topics/teams/articles/new-team
21. American Public Health Association. Community Health Workers. Accessed October 29, 2021. https://www.apha.org/apha-communities/member-sections/community-health-workers
CHW FAQs
1. North Carolina Department of Health and Human Services. Community Health Worker Training. Accessed October 29, 2021. https://www.ncdhhs.gov/divisions/office-rural-health/community-health-workers/community-health-worker-training
2. North Carolina Department of Health and Human Services (NC DHHS). Community Health Worker Initiative. Accessed October 29, 2021. https://www.ncdhhs.gov/about/department-initiatives/healthy-opportunities/community-health-worker-initiative
3. Sandhu B. The Value of Lived Experience in Social Change: The Need for Leadership and Organisational Development in the Social Sector. The Lived Experience; 2017. Accessed November 9, 2021. http://thelivedexperience.org/report/
4. Oxford Reference. lived experience. doi:10.1093/oi/authority.20110803100109997
5. University of North Carolina Chapel Hill, School of Social Work. Welcome to the NC Certified Peer Support Specialist Program. NC Peer Support Specialist Certification Program. Accessed November 9, 2021. https://pss.unc.edu/